Special Integrated Area Development Package for

North Waziristan

ADP Code: 191684

| APPROVAL STATUS | FORUM WITH DATE | PERIOD |  | PROJECT COST (Rs in Million) |
| --- | --- | --- | --- | --- |
|  |  | FROM | TO |  |
| Original | PDWP on 29-4-2020 | July: 2020 | June: 2023 | 2000.00 |
| 1st Neutral Cost Time Extension | Secretary P&DD 6th June, 2024 | 1st July, 2023 | 30th June, 2024 | 2000.00 |
| 2nd Neutral Cost Time Extension | Secretary P&DD 17th Feb, 2025 | 1st July, 2024 | 30th June, 2025 | 2000.00 |
| 1st Revision (Proposed) | PDWP on | July: 2024 | June: 2027 | 2,510.378 |

Sustainable Development Unit (SDU) Planning and Development Department Govt. of Khyber Pakhtunkhwa