GOVERNMENT OF PAKISTAN

PLANNING COMMISSION

PC-1 FORM

(PRODUCTION SECTORS)

- Name of the project

Surveillance on Pesticide and Fertilizer Adulteration in Khyber Pakhtunkhwa

- Location

The project head-office will remain at the Directorate of Soil and Plant Nutrition, ARI, Tarnab Peshawar. Project activities will be carried out at the following locations of the mentioned agro-ecological zones throughout the Province.

  - Central zones (Peshawar, Charsadda, Mardan, Swabi, Nowshera)

  - Eastern zones (Haripur, Abbottabad, Mansehra)

  - Southern Zones (Kohat, Karak, Bannu, DI Khan)

  - Northern Zones (Chitral, Dir Lower and Upper, Swat)

  - Coordinates of the ARI, Tarnab

| Location | Elevation (m) | Latitude (N) | Longitude (E) |
| --- | --- | --- | --- |
| ARI, Tarnab Peshawar | 308 | 33.58.542 | 071o41.611 |

- Authorities Responsible for

| - Sponsoring: | Agriculture, Livestock, Fisheries& Coop: Department Government of Khyber Pakhtunkhwa through ADP 2020-21 |
| --- | --- |
| - Execution: | Director General, Agriculture Research, Khyber Pakhtunkhwa |
| - Operation and maintenance: | Director, Soil & Plant Nutrition ARI, Tarnab, Peshawar |

| - (a) | Plan provision |  |
| --- | --- | --- |
|  | If the project is included in the medium term/five-year plan, specify actual allocation | NA |
|  | If not included in the current Plan, what warrants its inclusion and how is it now proposed to be accommodated. | The project is reflected in ADP 2020-21 at ADP# 15 Project ID# 200014 with total cost of Rs.250million for a period of three years (2020-21 to 2022-23) with current years’ allocation Rs.150 million. |

- If the project is proposed to be financed out of block provision, indicate:

| Total block provision | Amount already committed | Amount proposed for this project | Balance available |
| --- | --- | --- | --- |
| Nil | Nil | Nil | Nil |

Not Applicable.

4.  (b)   Provision in the current year PSDP/ADP

The proposed Project is included in the ADP 2020-21with a total cost of Rs.250 million and current year’s allocation of Rs.150

- Project objectives and its relationship with sector objectives:

The sector objectives (Vision 2025) for agriculture include:

- To bring about structural transformation of economy from low productivity to high productivity export oriented and globally competitive industry and services, and from agriculture to diversification in agro based industry.

- To transform agriculture and rural economy, ensure food and water security, value addition, research and modernization, promoting rural enterprises and best practices of water management.

- To achieve an annual average growth rate of 7 to 8 percent that is inclusive and endogenous as well, by bringing about knowledge-based science & technology driven and ICT intensive transformation, up scaling regional connectivity and intensifying entry into the global economy.

Sustainable Development Goals (SDGs):

The Government of Pakistan is committed to achieving Sustainable Development Goals (SDGs) set forth by the UN. Following SDGs are directly related with the objectives of the proposed project:

- SDG-1 (Poverty Reduction)

- SDG-2 (Zero Hunger)

- SDG-3 (Good Health)

- SDG-6 (Clean Water & Sanitation)

- SDG-11 (Sustainable Cities & Communities)

- SDG-12 (Responsible Consumption & Production)

- SDG-13 (Climate Action)

- SDG-14 (Life Below Water)

- SDG-15 (Life on Land)

Khyber Pakhtunkhwa Sustainable Development Strategy 2019-23:

The thematic areas pertaining to Agriculture, Food Security and Safe Environment of the strategy. The strategy identifies environmental problems one of the major challenges the Province face, which is besetting the sector, as dumping of untreated solid wastes, sewage and industrial effluents on land and water bodies are unregulated. Following objectives of the strategy are directly related with the objectives of the proposed scheme;

- Use of climate smart production technologies.

- Sustainable resources use management.

- Water and soil pollution control.

Specific objectives of the project are:

- To up-grade the existing analytical facility of the Directorate of Soil & Pant Nutrition, Agricultural Research Institute, Tarnab, Peshawar for checking adulteration of pesticides and fertilizers in the Province.

- To strengthen the Pesticide Residue Analysis Laboratory of the Directorate of SPN, ARI-Tarnab, for ensuring maximum residue level (MRL) in Fruit and Vegetable in compliance with Codex Alimentarius.

- To explore heavy metals in waters, soils crop/plants and agriculture produce specifically leafy and roots vegetables produced in the peri-urban areas of the Province.

- To establish bio-remediation facility for removal of heavy metals from wastewater and develop soil enhancer/bio-fertilizer for stabilization of heavy metals in soil.

- To enhance capacity of scientists, technical staff and extension workers and create awareness among farming communities consumers and processors.

- To provide basis for accreditation of analytical laboratories of the Directorate of SPN, ARI-Tarnab, Peshawar.

Quantitative Objectives of Project:

- Construction, renovation and up-gradation of Pesticides and Fertilizer Laboratory at Directorate of SPN, ARI-Tarnab, Peshawar.

- Methodology development for pesticide residue analysis of approximately 50 different pesticides of various groups in different matrices including fruits, vegetables, soil, water and honey from four zones of Khyber Pakhtunkhwa, 500 samples in total. - Analyses of approximately 1000 pesticide samples for possible adulteration from four zones of Khyber Pakhtunkhwa.

- Collection and analysis of approximately 1000 samples of various fertilizer products of different manufacturing companies from four zones of Khyber Pakhtunkhwa.

- Establishment of one bio-remediation structure at ARI, Tarnab for heavy metal removal from contaminated irrigation water.

- Development of soil enhancer/bio-fertilizer for improving soil health.

- Collection and analysis of approximately 500 samples (collectively) of wastewater, soil and plants/crops for heavy metal contamination from four ecological zones of Khyber Pakhtunkhwa.

- Nine number (09Nos.) of farmer field days/training and four numbers (04Nos.) of trainings to new recruited and existing technical staff will be conducted during the project period.

- Two numbers (02Nos.) of exposure visits of technical staff/scientist to renowned institutions of the country.

- Publication of 10000 pamphlets on project related topics.

6.	Description and justification of Project

(Describe the project and indicate existing facilities in the area and justify the establishment of the project.)

- (a) Description of Project

The economy of Pakistan is agro-based and is dependent on soil fertility for higher yield and production. The continuous mining through ages, climate change and without any material efforts for replenishment of these impoverished soils, have turned them into a state where they cannot nourish healthy crops. Therefore, it is important to find out ways and means for making these cultivated soils fertile and productive for getting higher crop yields to meet the demands of more food for the exploding population. In Pakistan various types of fertilizers and pesticides are used, some are locally manufactured and others are imported to boost up the production. However, there are several problems which are impeding the balance and efficient use of fertilizer and pesticides. These are non-availability of specific inputs at the right time, increasing prices, lack of proper amount and method of application and adulteration.

Worldwide demand of increased productivity as a result of growing population led the agricultural policy makers to utilize new technologies, not only to enhance food production but also to overcome certain hinders in the way of increasing productivity. Pests like weeds and other insects together cause high economical yearly loss (Gharde et al., 2018: Peshin and Dhawan, 2009). Pesticides use in agriculture is to regulate pests (Cloyd, 2012). Pesticides, an indispensable component of IPM, occupy a key position in boosting up agricultural production. This goal can only be achieved if the pesticides of standard quality are used. However, most of the generic pesticide products have been found inefficient in disease and pest control and the farmers suffer huge monetary losses due to their low quality. Keeping in view the situation pesticide Quality Control Lab was established in Directorate of Soil and Plant Nutrition, Agriculture Research Institute, Tarnab, Peshawar in 1996. As the name indicates this lab is responsible for pesticide formulation analysis. It is the only Lab of its nature in Khyber Pakhtunkhwa rendering services to farmers and all allied agencies in the province. Pesticide samples are drawn by the extension staff from the pesticide dealers and are sent to the laboratory for formulation analysis with the objective to ensure availability of quality pesticides to the farmers. In view of tremendous increase in the number of new products of new chemistry requires the monitoring of the products where suspicion arises, Unfortunately the existing facilities lack the capabilities to comply with the present-day demand therefore the existing facility of the pesticide formulation analysis is not sufficient to meet the requirements and needs further strengthening of the pesticide quality control program at provincial level.

No doubt the use of pesticides has increased agricultural production, the residues resulting from the misuse of pesticides is a major concern in many countries as well as in Pakistan. Several hundred pesticides of different chemical nature are used for agricultural and non-agricultural purposes in the country. Because of their widespread use, multi-residue analytical methods are needed for analyzing environmental and food samples which may contain residues of pesticides. The purposes of these analytical methods for the determination of pesticide residues in crops and food commodities include regulatory monitoring and enforcement, import/export certification, risk assessment, field application trials and marketing to consumers.

The increase in fertilizer use efficiency directly depending on fertilizer quality. At present, apart from some macro-fertilizers produced industrially, there are several mix macro, and micro-nutrient fertilizer, foliar fertilizer, plant growth regulator which are not controlled by Govt. They are circulated with of fertilizer arbitration organization; therefore, the farmers are always suffering from losses once having brought the adulterated or low-quality fertilizer, and the legitimate fertilizer producers and traders suffer from losses and risks. Fertilizers are not cheap input and therefore, it is essential that they should be efficiently used to produce maximum increase in crop yields and returned more to the farmers. A balance fertilization strategy is the only way to ensure a sustainable agriculture that can provide the country population with high quality food while, minimizing the impact on the environment. Balance fertilizer recommendation can only be made from high quality fertilizer. However, some of the fertilizer products are adulterated and lack its active ingredients mention on its label thus affecting the process of balance fertilization.

At present there are only two laboratories working on fertilizer quality analysis in Khyber Pakhtunkhwa. These laboratories are of technical and research nature exiting at ARI Tarnab (central zone) and ARI Swat (northern zone). Unfortunately, the existing facilities of fertilizer analysis are not sufficient to cover the whole province and to meet the requirements of new complex fertilizer thus requires up gradation of the laboratory and accreditation for standardizing it at provincial level. Presently, the fertilizer quality analysis is carried out in the same laboratory and instruments which are basically meant for soil and water analysis at ARI Tarnab Peshawar, thus increasing the load on one hand and affecting result precision on other hand. Thus, there is a dire need to establish a separate fertilizer quality analysis lab in Directorate of Soil and Plant Nutrition Peshawar.

Water is an essential component of life, but it is a susceptible and finite resource that has qualitative vulnerability and quantitative limitations. In the areas where fresh water is in short supply, wastewater is frequently used for crop irrigation. Agriculture is the most common area in which untreated wastewater is reused. According to an estimate in 2004, approximately 20 million ha is irrigated with wastewater in fifty countries worldwide (FAO Aqua Stat, 2017). Wastewater usage for crop irrigation has certain advantages such as providing the essential nutrients and organic matter, saving water and nutrients, and reducing cost of production (Zhang et al., 2017). However, waste water is contaminated with trace elements (Lead (Pb), Copper (Cu), Zinc (Zn), Cobalt (Co), Chromium (Cr), Nickel (Ni), Arsenic (As) many of which are non-essential and become toxic over time to plant, animals and human being. Long-term application of untreated wastewater resulted significant built up of heavy metal in soils, vegetables and subsequent transfer to food chain causing potential health risk to consumers (Khan et al., 2008: Singh et al., 2010).

Phyto-remediation is considered an effective, aesthetically pleasing, cost effective and environmentally friendly technology for the remediation of potentially toxic metals from the environment. Phyto-remediation follows different mechanisms such as phyto-extraction, phyto-stabilization, phyto-volatilization and rhizofiltration during the uptake or accumulation of heavy metals in the plant. Remediation of wastewater through constructed wetland has been magnificently executed over the last few decades worldwide as an appropriate management choice for wastewater. Constructed wetland (CW) is a biogeochemical and highly efficient system to treat wastewater generating from different sources such as domestic, highways, mining and industrial sectors. Phyto-remediation of heavy metal through constructed wetland will be carried out at ARI Tarnab, to provide safe and clean irrigation water to the farm land.

The central idea of the proposed project is also to upgrade comprehensive pesticide residue, fertilizers monitoring program and establishment of constructed wetland for phyto-remediation of heavy metal at provincial level. The training, educational, research and services activities are in line with public and private sectors dealing with food and environmental issues to meet their professional and advisory requirements.

### 6.  (b) Justification of Project

### The project “Surveillance on fertilizer and pesticide in Khyber Pakhtunkhwa” is designed with the aim to strengthen the research laboratories to augment the research work on soil quality and plant nutrition and to assess the fertilizer and pesticide adulteration with more precision and accuracy. Phyto-remediation of the heavy metals will also be addressed in the project.

The Directorate of Soil & Plant Nutrition since 1980 is actively involved in Laboratory analysis of soil, plant, fertilizer and pesticide samples from different R & D organizations, farmers, NGOs, Military Farms and research students from various universities. Fertilizer recommendation on the basis of soil test value to the farmer community is a routine job of this Directorate. These recommendations will only be fruitful if the fertilizers used are of quality in nature. This Directorate consists of 7 different sections with specific objective and mandate where pesticide Laboratory is responsible for pesticide analysis and formulation, soil chemistry section for soil, water and fertilizer analysis and recommendation to the end user. Beside this tremendous research work is carried out on food and soil quality, soil fertility, microbiology, plant nutrition and climate change assessment by their respective research section.

The total import of fertilizer during this period increased from 1.1 to 2.6 million tons. According to estimate of NFDC, 1996 about 5.5 million product tons of fertilizer were handled out of which 4.2 million tons was local production and rest were imported. Farmers have to spend over Rs 40.0 billion to purchase this quantity of fertilizer. All the effort will go waste, if the state does not ensure and guarantee the quality of fertilizers that are distributed amongst the farmers. Fertilizer is deregulated commodity, but need regulation in terms of distribution and quality. There exist some laws under fertilizer control act in the province but need a fresh look. A mushroom growth of products in different names is emerging and there is urgent need to develop institutional mechanism to test and validate these products before commercialization. For this purpose, fertilizer quality testing laboratory up gradation is proposed at Agriculture Research Institute Tarnab Peshawar This Lab will cover all the fertilizer samples from southern region (Kohat, Karak, Bannu, Lakki and DI Khan), eastern region samples (Haripur, Abbottabad, Mansehra) and centre region districts of KP i.e. Peshawar, Charsadda, Nowshehra, Mardan and Swabi.

Pesticides use in agriculture is to regulate pests (Cloyd, 2012). Pesticides, an indispensable component of IPM, occupy a key position in boosting up agricultural production. This goal can only be achieved if the pesticides of standard quality are used. However, most of the generic pesticide products have been found inefficient in disease and pest control and the farmers suffer huge monetary losses due to their low quality. Keeping in view the situation pesticide Quality Control Lab was established in Directorate of Soil and Plant Nutrition, Agriculture Research Institute, Tarnab, Peshawar in 1996. In view of tremendous increase in the number of new products of new chemistry requires the monitoring of the products where suspicion arises, Unfortunately the existing facilities lack the capabilities to comply with the present day demand therefore the existing facility of the pesticide formulation analysis is not sufficient to meet the requirements and needs further strengthening of the pesticide quality control program at provincial level. Besides this there is a huge need of establishing more similar kind of laboratories at Provincial level to involve more scientists in this task and to provide quick assistance as required.

The soil is the direct pathway for the contamination of plants by heavy metal via root uptake. Vegetables and crops irrigated by wastewater take up high concentrations of metals which may cause health risks to the users. In peri-urban regions of Pakistan, vegetables and crops are frequently irrigated by wastewater without any primary treatment. In different areas of Pakistan, the continuous use of wastewater for irrigation in the agricultural areas has caused a buildup of highly toxic metals compared to the soil irrigated by groundwater (Khan et al., 2013). Amin et al. (2014) reported that the Pb concentration in the soil irrigated by wastewater was four times higher than the soil irrigated by tube-well water in Mardan-Pakistan.

Generally, irrigation with wastewater elevates the total and available potentially toxic elements concentrations in soils. Heavy metals introduced into the soil via wastewater irrigation accumulate primarily in the surface layer and are generally more mobile and bioavailable than those released from the parent rocks (Cecchi et al., 2008). Therefore, heavy metal addition to the soil by wastewater application may represent more threats to plant contamination than natural sources of heavy metal contaminations.

Heavy metal pollution poses a serious threat to all forms of life in the environment due to the toxic effects of long-term environmental pollution. These metals are extremely sensitive at low concentrations and can be stored in food chain, posing a serious public health risk. Different organic pollutants and metals are not degradable and remain in their environment for a long time. Remediation using conventional physical and chemical methods is uneconomical and produces large volumes of chemical waste. The use of microorganisms is eco-friendly and cost-effective. Therefore, microorganisms have a variety of mechanisms of metal sequestration that hold greater metal biosorption capacities. For this purpose, a consultant will be required to isolate the viable strain of microorganism to remove or stabilize heavy metal in soil and reach its mobility to edible parts of crops.

Overall, the project will address the fertilizer and pesticide adulteration at provincial level and wastewater treatment for heavy metal at ARI Tarnab Peshawar.

EXISTING FACILITIES

Building:

The existing Pesticide and Soil Laboratories will be utilized for the sample analysis. Buildings for offices are already available at ARI-Tarnab, Peshawar.

Store/Laboratory:

Stores, laboratories and other facilities will be provided by the Directorate of Soil and Plant Nutrition ARI Tarnab, Peshawar. The available lab facility for fertilizer and pesticide is outdated and will be updated for accreditation purpose.

Staff:

The services of the Existing staff (Scientist and Laboratory Technicians) will be availed in this program and short-term training will be imparted to them in the local Research institutions.

Equipment and Machinery:

The Institute has somewhat latest equipment and machinery related to project activities. The project will need the required equipment and machinery to run project activities in this new area of research.

- Provide technical parameters i.e. input and output of the project in quantitative terms.  Also discuss the technology aspect of the project.

The project falls under priority areas of both federal Government as well as Government of Khyber Pakhtunkhwa. The project is directly related to the objective of developing the agricultural sector as reflected in the 9th five-year plan of the government of Khyber Pakhtunkhwa. The main objectives of the project are in line with the provincial Agricultural Policy, 2015. The project is fundamental importance and essential for the province to safe guard the farmer interest by ensuring quality of fertilizer and pesticide and implement environmentally friendly inputs to increase the per acre yield. The main objective of the agriculture sector is to increase the agriculture production of the province to meet the food requirement of the increasing population. Fertilizer and pesticide use are one of the main inputs. The judicious and balance use of fertilizer/pesticide based on quality laboratory test will help greatly to improve the country economy through higher yield and to meet the challenges of WTO constraints.

| S# | Input | Output |
| --- | --- | --- |
|  | Construction, renovation and up-gradation of Pesticides and Fertilizer Laboratory at Directorate of SPN, ARI-Tarnab, Peshawar. | Enhanced analytical capacity for pesticide and fertilizer quality analysis for quick results. |
|  | Methodology development for pesticide residue analysis of approximately 50 different pesticides of various groups in different matrices including fruits, vegetables, soil, water and honey from four zones of Khyber Pakhtunkhwa, 500 samples in total. | Developed mechanism for MRL value for various groups of pesticides in different matrices. Pesticides residue free food availability. |
|  | Analyses of approximately 1000 pesticide samples for possible adulteration from four zones of Khyber Pakhtunkhwa. | Minimizing the chance of adulteration in pesticide in local market |
|  | Collection and analysis of 1000 samples of various fertilizer products of different manufacturing companies from four zones of Khyber Pakhtunkhwa. | Adulteration cycle of various fertilizer products in Khyber Pakhtunkhwa will be tracked and checked. |
|  | Establishment of one bio-remediation structure at ARI, Tarnab for heavy metal removal from contaminated irrigation water. | Contamination of heavy metals in irrigation water is removed through bio-remediation for reducing health risks. |
|  | Development of soil enhancer/bio-fertilizer for improving soil health. | Increased yield and improved quality of crops. Stabilization of heavy metals in the soil. |
|  | Collection and analysis of 500 samples (collectively) of wastewater, soil and plants/crops for heavy metal contamination from four ecological zones of Khyber Pakhtunkhwa. | Identification and estimation of heavy metals contaminated places in the Province. |
|  | Five numbers (05Nos.) of farmer field days/workshops will be conducted during the project period. | Awareness among the farmers will be created. |
|  | Four numbers (04Nos.) of farmer’s trainings will be conducted during the project period. | Farmers will be trained about heavy metals, use of bio fertilizer and adulteration in the fertilizers and pesticides. |
|  | Four numbers (04Nos.) of trainings to new recruited and existing technical staff will be conducted during the project period. | Awareness among scientists and technical staff will be created and will be trained. |
|  | Two numbers (02Nos.) of exposure visits of technical staff/scientist to renowned institutions of the country. | Enhanced capacity of scientists and technical staff. |
|  | Publication of 10000 pamphlets on project related topics. | Mass awareness created. |

Methodology Proposed

Study 1: Pesticide Residues in Fruits/Vegetables and other matrices:

There is no regular pesticide residue monitoring program in the country. Even we have not developed our indigenous maximum residues limits (MRLs) to safeguard the interests of local farmers and consumer health. Several studies have testified that pesticide residues is a problem in Pakistan and if mitigating measures were not taken then it can pose consumer health risk, environmental concerns and international trade barriers. A certified laboratory is required to follow ISO 17025 guidelines and obtain International Accreditation. Unfortunately, the existing facilities lack the capabilities to comply with the present-day demand. The shall become focal point for all the pesticide residues related issues like methods development and validation, food and environmental samples monitoring, consumer health protection, advisory services and assisting in legislation on the subject in the province. The project shall provide an opportunity to the scientists of various establishments for increasing their capabilities with special reference to pesticide residue and quality analysis using developed gold techniques including GC-MS, LCMS-MS, GC-ECD-FID and HPLC-DAD.

This will pave the way for onward research in this field. So, researchers, university teachers and students will be direct beneficiaries. Thus, this project will provide a pool of trained manpower in this domain. A major part of the financial input goes to laboratory equipment. It is due to the fact that due to refined change in technology updated equipment has not been provided to already existing programs since long. The existing programs are not in a position to add/ replace equipment out of their normal budget or development grants due to resource constraints. The labs have to be structured to meet the requirement for accreditation according to ISO 17025 in terms of buildings, instruments, management and professional staff. This project will focus on implement quality assurance systems, providing technical advice, organizing training courses and comparative tests.

Monitoring of Pesticide Residues:

During survey for monitoring of pesticide residues, fresh samples of fruits/vegetables will be collected at harvest from farmers’ fields and provincial markets in major growing areas in Khyber Pakhtunkhwa to assess possible contamination status of the crop with pesticide residues before their release into market following Codex Alimentarius (FAO/WHO) protocols for sampling. All the samples will be transported immediately to the Pesticide residue laboratory and kept at -4oC until analysis in order to avoid any degradation of residues between sampling and analysis. These samples will be extracted, cleanup and will be analyzed using chromatographic techniques.

Pesticide quality control:

Pesticide samples will be drawn by the extension staff from the pesticide dealers and will be sent to the laboratory for formulation analysis with the objective to ensure availability of quality pesticides to the farmers. Where the samples will be stored and labeled. Their physical and chemical analysis will be performed and on the basis of their outcome results will be disseminate to the quarter concern.

Study 2: Fertilizer Adulteration Assessments:

The use of mineral fertilizers is among the key factors driving the increased global agricultural production required to feed the rising human population. Synthetic N fertilizer produces roughly half of today’s world food (Erisman et al., 2008). Depending on food demand, the projected consumption of N fertilizer is likely to change from current 105 Million tons (MT) to 180 MT, Phosphate from 40 MT to 80 MT and Potash from 29 MT to 32 MT (Sutton et al. 2013).

In Pakistan, about 70 % of the farmers in rural area directly engaged in agriculture sector. The sustainable increase in agricultural productivity and rural incomes are the basis for broad-based economic growth. The central challenge however remains how best to create conditions under which farmers can intensify their production and increasingly link them to markets. Achieving this will help reduce food insecurity in the country. The research showed that country would not achieve food security and sustainable productivity without balance and rational use of fertilizers. Pakistan soils are much depleted having inherent low fertility and organic matter. The continuous cropping further aggravated the problems and cause mining of major and micronutrients in soil. This depletion of nutrients suggests that efficient use of fertilizers would be required to maintained soil fertility.  The Govt: recognizes the effective role of fertilizer in agricultural productivity and achieving national food security. Farmer throughout the country must have accesses to the quality fertilizer at reasonable cost. The fertilizer should be appropriate for local condition, effective in use and according to quality standards as per label on packaging. The total fertilizer productions in Pakistan during 2018-19 were 7824 thousand tons by 14 production units while imports of fertilizer during same periods were 1896 thousand tons (NFDC, 2020). The concerned about the adulterated fertilizer has been increasing by farmers causes big monetary losses to the individual farmers and national economy. For this purpose, a comprehensive survey will be made to access the fertilizer adulteration in Khyber Pakhtunkhwa. The fertilizer sampling will be done at 3 stages for each major fertilizer brand i.e. at manufacturing level, distribution and retailer level with coordination with Agriculture Extension. These samples will be analyzed for quality nutrient concentration in the upgraded fertilizer laboratory and report will be prepared accordingly. This will enable the understanding to access the adulteration or mixing of fertilizer in different brands in different locations of the province and to devise a viable strategy for its control and to provide quality fertilizer product to the farmers.

Brand to be surveyed

  - Urea (Prepared by various pvt companies as FFC, Engro, Fathma Fertilizer etc).

  - DAP (Pak Arab, FFC, Engro, Fathma Fertilizer etc)

  - NP (Engro, Pak Arab, Fatima Fertilizer etc)

  - SSP (Engro, Agri Tech, Suraj Fertilizer etc)

  - SOP (Engro, FFC etc)

  - AS (Engro, Import)

  - NPK (Engro Fertilizer)/Others (micronutrient fertilizers)

Area to be sampled

  - Central zones (Peshawar, Charsadda, Mardan, Swabi, Nowshera)

  - Eastern zones (Haripur, Abbottabad, Mansehra)

  - Southern Zones (Kohat, Karak, Bannu, DI Khan)

  - Northern Zones (Chitral, Dir Lower and Upper, Swat)

Study 3: Heavy Metal Management in Wastewater

Water is an essential component of life, but it is a susceptible and finite resource and 60% world’s population may face the problem of a water shortage by the year of 2025 (Rijsberman, 2006). In the areas where fresh water is in short supply, wastewater is frequently used for crop irrigation.

Agriculture is the most common area in which untreated wastewater is reused. The municipal wastewater demand corresponds to 11% of the water withdrawal, globally (FAO, 2017), which is potentially irrigating almost 40 million ha or 15% of all irrigated lands.

The volume of wastewater generated by domestic, industrial and commercial sources are increasing with population, urbanization, improved living condition and economic development (Qadir et al., 2008). Wastewater usage for crop irrigation has certain advantages such as providing the essential nutrients and organic matter, saving water and nutrients, and reducing cost of production (Zhang et al., 2017). Wastewater provides a nutrient enriched source for irrigation and farmers in Pakistan usually prefer wastewater even when freshwater is available, because they earn higher profits using wastewater. Wastewater are contaminated with heavy metal [Lead (Pb), Copper (Cu), Zinc (Zn), Cobalt (Co), Chromium (Cr), Nickel (Ni), Arsenic (As)] many of which are non-essential and become toxic over time to plant, animals and human beings. Long-term application of untreated waste water resulted significant built up of heavy metals in soils, vegetables and subsequent transfer to food chain causing potential health risk to consumers (Khan et al., 2008: Singh et al., 2010). Many of the research work carried out in Khyber Pakhtunkhwa; identify the heavy metal in vegetable and fruit plants. However, less work has been done on management of heavy metal in farm field.

Keeping in view of the bad quality of wastewater and its impact on crop plants grown on soils irrigated with wastewater at Peshawar, bioremediation facility for the removal of heavy metals from wastewater through useful plants, will be carried out Agricultural Research Institute, Tarnab in technical collaboration with NARC, Islamabad. The heavy metal removal efficiency of various aquatic plants will be assessed in Lab and based on research data, the structure will be recommended for purification of various domestic and industrial wastewaters (Proposed Drawing Map of Wet Land Facility for Peshawar is attached at page No.). Similarly, survey will be carried out in selected districts of KP for heavy metal assessment in waste water, soil and crops.

The Directorate of Soil and Plant Nutrition has achieved many goals in eliminating the soil problems and established fertilizer recommendations for fruit, vegetables and cereal crops in almost every district of the province. The soil chemistry section is involved in assessment of fertilizer quality, heavy metal in fruit and vegetables and irrigation water quality. The pesticide section is actively involved in pesticide quality assessment and pesticide residue assessment in fruit and vegetables. Through this project, the laboratories of different sections will be upgraded and enable it for quality research on new topics through modern instrumentation. The results will be more precise as per ISO standard and meet the challenges of WTO and millennium development goals. The Directorate will be jumped in new area of research and be able to analyzed micronutrients fertilizer, heavy metal in wastewater and pesticide residue monitoring in fruit and vegetables for the first time.

Study 4: Development of Soil Enhancer/ Bio-Fertilizer:

Plants need inorganic raw material or nutrients for their growth and development. Soil fertility is of prime importance to increase productivity of field crops. It refers to the ability of soil to supply all the essential nutrients in optimum amount to the plants. Sometime nutrients are present in soil but not available to the plants due to certain restricted soil condition such as alkaline or water lodged condition, poor soil properties and poor microbial activities. All these factors affect plant growth and soil productivity. Most of our soils are alkaline having high pH, calcareous in nature, low organic matter and low water and nutrient holding capacity. Under such condition, most of the nutrients are not available to the plants rather they are fixed with clay mineral, leached down below root zone and contaminate ground water or losses to the atmosphere causing environmental problems. To overcome this problem, some of the beneficial and eco-friendly strain of fungi are available that are able to increase the root hairs and deep root roots penetration in soil and thus enhance the absorptive surface area of plants for nutrients and water. Plants with deep root system are better able to extract water and nutrients from deeper soil zone and resist diseases and water stress. These fungi use soil organic matter as food source and establishes itself with plant roots and the surrounding soil. During this process the fungi increase the fermentation of soil organic matter and solubilize the fixed soil nutrients to the plants. Also, the fungal biomass stored soil nutrients which are available to plants on their decay and protect these nutrients from leaching and other losses. Also, heavy metal pollution poses a serious threat to all forms of life in the environment due to the toxic effects of long-term environmental pollution. These metals are extremely sensitive at low concentrations and can be stored in food chain, posing a serious public health risk. Different organic pollutants and metals are not degradable and remain in their environment for a long time. Remediation using conventional physical and chemical methods is uneconomical and produces large volumes of chemical waste. The use of microorganisms is eco-friendly and cost-effective. Therefore, microorganisms have a variety of mechanisms of metal sequestration that hold greater metal bio-sorption capacities. For this purpose, a Research Officer (Bio-Fertilizer) will be hired for the project life to isolate the viable strain of microorganism to remove or stabilize heavy metal in soil, solubilize the tightly bound nutrients and improve the efficiency of soil applied inputs. Following will be terms of reference for the Research Officer (Bio-Fertilizer) for the development of micro-organism-based soil enhancer/bio-fertilizers;

- The Research Officer (Bio-Fertilizer) shall have professional degree in plant pathology/soil Science (microbiology) and have experience in development of soil micro-organism based soil enhancer/bio-fertilizer.

- The Research Officer (Bio-Fertilizer) will isolate suitable and viable strain of soil microbe(s) best suited to the agro-environment of the Province.

- The Research Officer (Bio-Fertilizer) will develop mechanism for viable procedure for bio multiplication of the isolated microbe(s) and soil application method and dose of the final product.

- The Research Officer (Bio-Fertilizer) will develop comprehensive report enunciating the technology and methodology of the product.

- The Research Officer (Bio-Fertilizer) will trained and impart the technology to the scientists for sustainability.

- Provide details of civil works, equipment, machinery and other physical facilities required for the project.

- Equipment/Machinery and Other Physical Facilities:

- Exposure Visit (Annexure-I)

- Training for 25 Participants at ARI Tarnab (Annexure-II)

- Training for 25 Participants at Farmer Field (Annexure-III)

- List of Pesticide Standards and Laboratory Chemicals (Annexure-IV)

- List of IT Equipment (Annexure-V)

- Laboratory Equipment (Annexure-VI)

- Vehicles (Annexure-VII)

- List of furniture (Annexure-VIII)

- Laboratory Glassware (Annexure-IX)

- Establishment of Bioremediation Wastewater treatment facility Peshawar (Annexure -XI)

- Office Equipment and others (Annexure XII)

Governance Issues Relevant to the Project and Strategy to resolve them

The Khyber Pakhtunkhwa Agricultural Research System has well established hierarchy and all the research and development work is carried out in a systematic way. The scientists have the capacity and capabilities to make the environments sound for R&D. It is hoped that no such governance issue will arise with in project life or if any issue arises then the Director General, Agri. Research and the Secretary of the department will resolve them under the prevailing rules and regulations.

- Capital cost estimates

  - Total cost of the Project:				Rs. 233.903 million

Revenue:					Rs. 219.717 million

Capital:					Rs. 14.186 million

  - Indicate date of estimation of project cost:	August, 2020

  - Basis of determining the capital cost estimates: MRS, 2020

### Provide year-wise estimation of physical activities as per following:

ANNUAL PHASING AND DETAIL OF PROJECT ACTIVITIES

| Component wise, year wise Annual Activities |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S# | Items | Unit | 2020-21 | 2021-22 | 2022-23 | Total |
| 1 | Construction, renovation and up-gradation of Pesticides and Fertilizer Laboratory at Directorate of SPN, ARI-Tarnab, Peshawar. | % | 50 | 50 | -- | 100 |
| 2 | Methodology development for pesticide residue analysis of approximately 50 different pesticides of various groups in different matrices including fruits, vegetables, soil, water and honey from four zones of Khyber Pakhtunkhwa, 500 samples in total (page No. 60). | % | 20 | 40 | 40 | 100 |
| 3 | Analyses of approximately 1000 pesticide samples for possible adulteration from four zones of Khyber Pakhtunkhwa (page No. 61). | Nos. | 200 | 400 | 400 | 1000 |
| 4 | Collection and analysis of approximately 1000 samples of various fertilizer products of different manufacturing companies from four zones of Khyber Pakhtunkhwa (page No. 61). | Nos. | 200 | 400 | 400 | 1000 |
| 5 | Establishment of one bio-remediation structure at Peshawar for heavy metal removal from contaminated irrigation water (page No. 67-70). | % | 50 | 50 | -- | 100 |
| 6 | Development of soil enhancer/bio-fertilizer for improving soil health. | % | 20 | 40 | 40 | 100 |
| 7 | Collection and Analysis of approximately 500 samples (collectively) of wastewater, soil and plants/crops for heavy metal contamination from four ecological zones of Khyber Pakhtunkhwa (page No. 62). | Nos. | -- | 250 | 250 | 500 |
| 8 | Five numbers (05Nos.) of farmer field days/workshops will be conducted during the project period. | Nos. | 1 | 2 | 2 | 5 |
| 9 | Four numbers (04Nos.) of farmer’s trainings will be conducted during the project period. | Nos. | 1 | 2 | 1 | 4 |
| 10 | Four numbers (04Nos.) of trainings to new recruited and existing technical staff will be conducted during the project period. | Nos. | 1 | 2 | 1 | 4 |
| 11 | Two numbers (02Nos.) of exposure visits of technical staff/scientist to renowned institutions of the country. | Nos. | 0 | 1 | 1 | 2 |
| 12 | Publication of 10000 pamphlets on project related topics. | Nos. | -- | 5000 | 5000 | 10000 |

Year-wise/Component-wise financial phasing 233.903 (Million Rupees)

| S# | Object Codes | 2020-21 | 2021-22 | 2022-23 | Total |
| --- | --- | --- | --- | --- | --- |
| A | ESTABLISHMENT BUDGET |  |  |  |  |
|  | Additional Charge Allowance @ 20 % of the basic pay |  |  |  |  |
| 1 | Director SPN (1) | 0.144 | 0.144 | 0.144 | 0.432 |
| 2 | Senior Research Officers (2) | 0.184 | 0.197 | 0.211 | 0.592 |
| 3 | Research Officer (4) | 0.292 | 0.312 | 0.336 | 0.940 |
| 4 | Office Assistant (1) | 0.044 | 0.048 | 0.052 | 0.144 |
| 5 | Senior Clerk (1) | 0.036 | 0.04 | 0.044 | 0.120 |
| 6 | Junior Clerk (2) | 0.06 | 0.064 | 0.068 | 0.192 |
|  | Sub total | 0.760 | 0.805 | 0.855 | 2.420 |
|  | DPL |  |  |  |  |
|  | Research Officer (will be hired as per Project policy) | 1.080 | 1.134 | 1.191 | 3.405 |
| 7 | Internees @ 25000/month | 1.440 | 1.440 | 1.440 | 4.320 |
| 8 | Daily Paid Staff @673/day | 1.000 | 2.000 | 2.000 | 5.000 |
|  | Sub total | 3.520 | 4.574 | 4.631 | 12.725 |
|  | Establishment total | 4.280 | 5.379 | 5.486 | 15.145 |
| B | OPERATIONAL BUDGET |  |  |  |  |
| 1 | Postage and Telegraph | 0.010 | 0.010 | 0.010 | 0.030 |
| 2 | Telephone and Internet | 0.150 | 0.150 | 0.100 | 0.400 |
| 3 | Gas | 0.100 | 0.150 | 0.150 | 0.400 |
| 4 | Electricity | 0.100 | 0.250 | 0.250 | 0.600 |
| 5 | Vehicle Registration | 0.000 | 0.300 | 0.000 | 0.300 |
| 6 | TA/DA | 0.500 | 1.500 | 0.500 | 2.500 |
| 7 | POL charges of vehicles, tractors and others | 1.000 | 2.000 | 2.000 | 5.000 |
| 8 | Stationery | 0.300 | 0.300 | 0.400 | 1.000 |
| 9 | Printing and Publications | 0.400 | 0.700 | 0.400 | 1.500 |
| 10 | Advertisement and publicity | 0.300 | 0.350 | 0.350 | 1.000 |
| 11 | Transportation of goods | 0.250 | 0.300 | 0.300 | 0.850 |
| 12 | Others | 0.250 | 0.500 | 0.250 | 1.000 |
| Operational Cost Total |  | 3.360 | 6.510 | 4.710 | 14.580 |
| C | PROGRAM COST |  |  |  |  |
| 1 | Exposure Visits (02 Nos) (Annexure-I) | 0.000 | 0.220 | 0.220 | 0.440 |
| 2 | Farmers trainings at ARI, Tarnab-Peshawar (Annexure-II) | 0.093 | 0.186 | 0.093 | 0.372 |
| 3 | Scientists trainings at ARI, Tarnab-Peshawar (Annexure-II) | 0.093 | 0.186 | 0.093 | 0.372 |
| 4 | Framers field days (Annexure-III) | 0.143 | 0.286 | 0.286 | 0.715 |
| 5 | Purchase of Laboratory equipment (Annexure-VII) | 103.498 | 32.726 | 0.000 | 136.224 |
| 6 | Purchase of Glass wares and laboratory kits (Annexure-X) | 3.394 | 3.039 | 0.000 | 6.433 |
| 7 | Establishment of Bioremediation Facility (Annexure-XI) | 3.134 | 0.000 | 0.000 | 3.134 |
| 8 | Chemicals, Pesticide standards and solvents as per table (Annexure - IV and V) | 7.290 | 9.213 | 1.000 | 17.503 |
| Program Cost Total |  | 117.645 | 45.856 | 1.692 | 165.193 |
| D | PHYSICAL ASSETS |  |  |  |  |
| 1 | Purchase of IT equipment (Annexure-VI) | 2.000 | 0.805 | 0.000 | 2.805 |
| 2 | Conversion from single to Double Cabin Annexure-VIII) | 2.600 | 0.000 | 0.000 | 2.600 |
| 3 | Single Cabin (4x4) Convertible (Annexure-VIII) | 6.000 | 0.000 | 0.000 | 6.000 |
| 4 | Single Cabin (4x2) Convertible (Annexure-VIII) | 4.500 | 0.000 | 0.000 | 4.500 |
| 5 | Purchase of furniture and fixtures (Annexure-IX) | 2.055 | 0.000 | 0.000 | 2.055 |
| 6 | Office Equipment and others (Annexure XII) | 1.560 | 1.780 | 0.000 | 3.340 |
| Physical Assets Total |  | 18.715 | 2.585 | 0.000 | 21.300 |
| E | CIVIL WORKS |  |  |  |  |
| 1 | Civil works + Solarization | 5.000 | 9.186 | 0.000 | 14.186 |
| Civil work Total |  | 5.000 | 9.186 | 0.000 | 14.186 |
| F | REPAIRS AND MAINTENANCE |  |  |  |  |
| 1 | Transport | 0.500 | 0.250 | 0.250 | 1.000 |
| 2 | Plant and machinery | 0.000 | 0.250 | 0.250 | 0.500 |
| 3 | Laboratory equipment's | 0.300 | 0.500 | 0.800 | 1.600 |
| 4 | Furniture | 0.200 | 0.200 | 0.000 | 0.400 |
| Repair and Maintenance Total |  | 1.000 | 1.200 | 1.300 | 3.500 |
|  | GRAND TOTAL | 150.000 | 70.716 | 13.188 | 233.903 |

Budget Summary

| S # | Object Codes | 2020-21 | 2021-22 | 2022-23 | Total |
| --- | --- | --- | --- | --- | --- |
| A | Establishment total | 4.280 | 5.379 | 5.486 | 15.145 |
| B | Operational Cost Total | 3.360 | 6.510 | 4.710 | 14.580 |
| C | Program Cost Total | 117.645 | 45.856 | 1.692 | 165.193 |
| D | Physical Assets Total | 18.715 | 2.585 | 0.000 | 21.300 |
| E | Civil work Total | 5.000 | 9.186 | 0.000 | 14.186 |
| F | Repair and Maintenance Total | 1.000 | 1.200 | 1.300 | 3.500 |
|  | Grand Total | 150.000 | 70.716 | 13.188 | 233.903 |

(Million Rupees)

- Annual Operating Cost for One Year after completion of the Project

| Item | Cost (million) |
| --- | --- |
| Establishment Expenses | 2.000 |
| Operating Expenses | 8.410 |
| Total Repair and Maintenance | 2.300 |
| Total | 12.710 |

- Demand and Supply Analysis

Not applicable to Research Projects.

10.	Financial Plan and Mode of Financing

Sources of financing

(a)	Equity:

Indicate the amount of equity to be financed from each source

- Sponsors own resources	NA

- Federal government 		NA

- Provincial government Rs. 250 million through ADP.

- DFI's/banks 			NA

- General public 		NA

- Foreign equity (indicate partner agency) NA

- NGO’s/beneficiaries		NA

- Others				NA

b)	Debt

Indicate the local & foreign debt, interest rate and grace period and repayment period for each loan separately.  The loan repayment schedule is also annexed.	NA

c)	Grants along with sources			NA

d)	Weighted cost of capital			NA

- Project benefits and analysis

### a.   Project Benefits

### Financial:

It is too early to quantify the financial benefits from this project, but it can safely be estimated that once fully operational, this project will enable the government of KPK to save in millions on the import and purchase of costly pesticides/insecticides. Judicial use of fertilizers and pesticides will reduce the burden on import of these fertilizers and pesticides.

Social:  Benefits to the Target Group.

Farmers are mainly concerned about the private cost of pesticide/fertilizer they have to incur to achieve desirable outputs and are least concerned about the undesirable byproducts of their production processes. The continuous monitoring of pesticides and fertilizers will save foreign exchange and time that could be incurred if the samples are to be analyzed outside the country. This will support trade in WTO/SPS/SBT measures. It is accepted that the Pakistan is facing challenges of pesticides/fertilizers undesired outputs, However, these issues, besides quality of pesticides/fertilizers are also linked to improper selection of these inputs, improper application time and spraying without keeping in mind their side effects and use of faulty spraying techniques. In addition, the grower’s needs information on the climate change, insurgence of new pests and knowledge of the new registered chemistries, to ensure efficient crop protection.

Environmental impact assessment

The project will have direct positive impact on environment by analyzing environmental samples and evaluating the impact of pollutants on the environments. Moreover, awareness creation among the general public about the environmental issues particularly agro chemicals (POPS) will be the integral part of the activities of proposed setup in the long run.

(b).   Project analysis

Quantifiable output of the project

Quantitative output of the technologies developed under the project cannot be quantified. However, the information generated by the project will be utilized by the farmers for increasing their yield quantitatively and qualitatively. This will increase not only the income of the farmers but also enhance the income of the Govt. including foreign exchange.

Unit Cost analysis

The proposed project is mainly focusing on fertilizers, pesticides adulteration and remediation of waste water activities involving many indirect out puts and benefits, hence assigning monetary values to inputs and particularly outcomes in social sector programs are rarely so simple, and it is not always appropriate to do so.

Employment Generation (direct and indirect)

Once such activities (Pesticide, fertilizer and heavy metal analysis) will gear up, private sector will jump into the field and thus a big avenue will be opened for employment.

SENSITIVITY ANALYSIS

Impact of delays on project cost and viability

Delayed approval of the project and non-availability of funds as per financial phasing of PC-1 may affect the project execution because the market may go up so the purchase of equipment, chemical, glassware and other accessories may suffer.

SWOT Analysis of Soil & Plant Nutrition Directorate, ARI, Tarnab, Peshawar

| S.No | Strengths |
| --- | --- |
| 1 | Highly qualified, well trained and experienced Lab technical staff. |
| 2 | Multidisciplinary research teams with legitimate approaches to farmer problems. |
| 3 | A network of well distributed labs in Khyber Pakhtunkhwa. |
| 4 | Tremendous experience of working with foreign donor projects. |
| 5 | Made significant contributions through successful project implementation like SCARP, at selected locations around Khyber Pakhtunkhwa. |
| Weaknesses |  |
| 1 | Poor service structure for lab technical staff. |
| 2 | Limited exposure of research staff for modern lab equipment’s. |
| 3 | The pesticide and fertilizer quality assessment are limited to ARI, Tarnab in whole province. |
| 4 | The lab. methods evaluation and protocols development are too much time consuming |
| 5 | The old lab. equipment, electricity failure, gas and water shortage effect timely results and precision |
| 6 | The non-function nature of most soil labs. in province increase the analysis load on this Directorate. |
| 7 | Poor in-service training for lab technical staffs and researchers. |
| 8 | Lack the analysis facilities for Micro-Nutrients fertilizer/heavy metal in wastewater/ residue analysis of Pesticides. |
| Opportunities |  |
| 1 | Great chances to jump in new area of research in micro-nutrients analysis, heavy metal contamination and pesticide residues analysis. |
| 2 | Potential for improved analytical skill of lab staff. |
| 3 | Excellent opportunities for collaboration with public research and R & D organization, private companies. |
| 4 | Opportunities for capacity building and human resource development. |
| 5 | Great opportunities for Exportable food items to improve quality. |
| 6 | Greater opportunity for contaminated wastewater bioremediation through least capital investment. |
| 7 | Quality life through reduce health risk. |
| 8 | Quite useful for climate smart technology adoption and reduce environmental pollution. |
| 9 | The existing wider yield gap is also a great opportunity through use of low standard Agricultural products. |
| Threats |  |
| 1 | Withdrawal from financial assistance. |
| 2 | Prevailing economic situation of country will increase budgetary allocations. |
| 3 | Instability in macro-economic and political environment. As a result prices of importable lab equipment increase. |
| 4 | Unstable socio-political environment may reduce the sample collection |
| 5 | Unpredictable fuel/electric supplies and public strikes can discontinue research Lab activities at critical stages. |

12.	Implementation of the project

- Indicate starting and completion date of the project

Commencement Date: July, 2020

Completion Date:	30th June 2023

| Activity/Year | Year-1 |  |  |  | Year-2 |  |  |  | Year-3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Construction, renovation and up-gradation of Pesticides and Fertilizer Laboratory at Directorate of SPN, ARI-Tarnab, Peshawar. |  |  |  |  |  |  |  |  |  |  |  |  |
| Methodology development for pesticide residue analysis of approximately 50 different pesticides of various groups in different matrices including fruits, vegetables, soil, water and honey from four zones of Khyber Pakhtunkhwa, 500 samples in total (page No. 60). |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyses of approximately 1000 pesticide samples for possible adulteration from four zones of Khyber Pakhtunkhwa (page No. 61). |  |  |  |  |  |  |  |  |  |  |  |  |
| Collection and analysis of approximately 1000 samples of various fertilizer products of different manufacturing companies from four zones of Khyber Pakhtunkhwa (page No. 61). |  |  |  |  |  |  |  |  |  |  |  |  |
| Establishment of one bio-remediation facility at Peshawar for heavy metal removal from contaminated irrigation water. |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of soil enhancer/bio-fertilizer for improving soil health. |  |  |  |  |  |  |  |  |  |  |  |  |
| Collection and analysis of approximately 500 samples (collectively) of wastewater, soil and plants/crops for heavy metal contamination from four ecological zones of Khyber Pakhtunkhwa (page No. 62). |  |  |  |  |  |  |  |  |  |  |  |  |
| Five numbers (05Nos.) of farmer field days/workshops will be conducted during the project period. |  |  |  |  |  |  |  |  |  |  |  |  |
| Four numbers (04Nos.) of farmer’s trainings will be conducted during the project period. |  |  |  |  |  |  |  |  |  |  |  |  |
| Four numbers (04Nos.) of trainings to new recruited and existing technical staff will be conducted during the project period. |  |  |  |  |  |  |  |  |  |  |  |  |
| Two numbers (02Nos.) of exposure visits of technical staff/scientist to renowned institutions of the country. |  |  |  |  |  |  |  |  |  |  |  |  |
| Publication of 10000 pamphlets on project related topics. |  |  |  |  |  |  |  |  |  |  |  |  |

Based Monitoring (RBM) Framework indicators in quantifiable terms

| S. No. | Input | Output | Outcome |  | Targeted impact |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Baseline Indicator | Targets after Completion |  |
| 1 | Construction, renovation and up-gradation of Pesticides and Fertilizer Laboratory at Directorate of SPN, ARI-Tarnab, Peshawar. | Enhanced analytical capacity for pesticide and fertilizer quality analysis for quick results. | Due to the lack modern instrumentation, the analytical work is limited to few old laboratory equipment and facilities. | The analytical capacity will be increase manifold. The Directorate will be jumped in to a new era of research (heavy metal, micro nutrient, pesticide residue analysis). | Availability of pesticide residue free food for general public and export purposes. Quality products of pesticides and fertilizer for farmers of the Province. Reducing harmful impact on environment through cleaning of contaminated water. |
| 2 | Methodology development for pesticide residue analysis of approximately 50 different pesticides of various groups in different matrices including fruits, vegetables, soil, water and honey from four zones of Khyber Pakhtunkhwa, 500 samples in total. | Developed mechanism for MRL value for various groups of pesticides in different matrices. Pesticides residue free food availability. | No previous research has been conducted in the province. | Bench mark for 50 different pesticides residues will be developed first time in the province, 500 samples in total. | Safe food will be available to the end user and for export. The MRL based fruits and vegetables will provide a base line indicator. |
| 3 | Analyses of approximately 1000 pesticide samples for possible adulteration from four zones of Khyber Pakhtunkhwa. | Minimizing the chance of adulteration in pesticide in local market | 200 | Quality assessment of newly emerging pesticides will be possible throughout the province. | Quality inputs will be available for the farming community |
| 4 | Collection and analysis of approximately1000 samples of various fertilizer products of different manufacturing companies from four zones of Khyber Pakhtunkhwa. | Adulteration cycle of various fertilizer products in Khyber Pakhtunkhwa will be tracked and checked. | 150 | Four zones of the province will be served and analyzed for quality of macro and micro fertilizers. | Farmers income will be enhanced through availability of quality fertilizer. Environment will be protected through reducing low standard fertilizer. |
| 5 | Establishment of one bio-remediation facility at Peshawar for heavy metal removal from contaminated irrigation water. | Contamination of heavy metals in irrigation water is removed through bio-remediation for reducing health risks. | No previous research has been conducted in this regard. | Wastewater will be cleaned from various heavy metals and pollutants. | Clean irrigation water from toxic metal will be available for sowing of different fruits, vegetable and other crops. |
| 6 | Development of soil enhancer/bio-fertilizer for improving soil health. | Increased yield and improved quality of crops. | Limited work has been made in this very important technology. | Safe organic fertilizer will be available to the farmer. | Improve soil health and crop quality. |
| 7 | Collection and analysis of approximately500 (collectively) samples of wastewater, soil and plants/crops for heavy metal contamination from four ecological zones of Khyber Pakhtunkhwa. | Identification and estimation of heavy metals contaminated places in the Province. | No such facility of analysis of heavy metals is available at the movement. | Heavy metal will be assessed in soil, vegetables and field crops. | The most contaminated area of the province will be identified and suggested remedy. |
| 8 | Five numbers (05Nos.) of farmer field days/workshops will be conducted during the project period. | Awareness among the farmers will be created. | NA | Farmers, field staff and technical staff will gain knowledge regarding the safe use of pesticides and fertilizers | General public and farmers will get awareness regarding safe use of pesticides, fertilizers and wastewater uses |
| 9 | Four numbers (04Nos.) of farmer’s trainings will be conducted during the project period. | Farmers will be trained about heavy metals, use of bio fertilizer and adulteration in the fertilizers and pesticides. | NA | Farmers and field staff will gain knowledge regarding the safe use of pesticides and fertilizers | General public and farmers will get awareness regarding safe use of pesticides, fertilizers and wastewater uses |
| 10 | Four numbers (04Nos.) of trainings to new recruited and existing technical staff will be conducted during the project period. | Awareness among scientists and technical staff will be created and will be trained. | NA | Scientists and technical staff will gain knowledge regarding the safe use of pesticides and fertilizers | General public, scientists and technical staff will get awareness regarding safe use of pesticides, fertilizers and wastewater uses |
| 11 | Two numbers (02Nos.) of exposure visits of technical staff/scientist to renowned institutions of the country. | Enhanced capacity of scientists and technical staff. | Nil | Will boost the analytical techniques of the scientists and other technical staffs. | High skilled staff will be available for analysis and training to the growers regarding safe use of pesticides, fertilizers and waste water uses. |
| 12 | Publication of 10000 pamphlets on project related topics. | Mass awareness created. | Nil | 10000 Nos. of brochures distributed for awareness of the growers and general public of KP. | Sensitization regarding safe use of fertilizers and pesticides. |

13. 	Management structure and manpower requirements including 	specialized skills during execution and operational phases

Administrative arrangements for implementation of the project

The project will be operated by the P.I of the project who will be the Director Soil and Plant Nutrition, ARI, Tarnab, Peshawar. He will get Additional charge allowance. He will be the over all in-charge of the project having drawing and disbursing powers. He will recruit all the staff of the project according to standing rules and policy. He will declare three Senior Research Officers as focal persons for three sub components in addition to their own duties. They will implement project activities according to directions given by PI, they will prepare and submit their relevant reports to PI of the project. They will get additional charge allowance from the project as per policy.

The manpower required of skills/professionals during execution and operation of the Project

The following manpower (Technical/Professional, skilled and non-skilled) will be required for the execution and operation of the proposed Project. For effective implementation and smooth running of the proposed project, some of the existing officers, officials and laboratory staff will also be engaged in the project activities.

EXISTING STAFF REQUIRE FOR THE PROJECT ACTIVITIES

| Nomenclature of Post | BPS | Nos. of posts | TORs |
| --- | --- | --- | --- |
| Director, SP&N/PI of the project | 19 | 1 | He will be the Project Incharge/Principal Investigator and will supervise project activities in the different sections of the Directorate. Additional charge allowance will be paid from the project. |
| Senior Research Officers | 18 | 2 | The incumbents are working in the SP&N Directorate. Their services will be available to assist the principal investigator, an additional duty along with his own sectional activities. Additional charge allowance will be paid from the project. |
| Research Officers | 17 | 4 | The incumbents are working in the SP&N Directorate. Their services will be available to assist the principal investigator, an additional duty along with his own sectional activities. Additional charge allowance will be paid from the project. |
| Office Assistant/Accountant | 14 | 1 | The incumbents are working anywhere conducive to help the P.I may be in addition to his own duties. Additional charge allowance will be paid from the project |
| Senior clerk | 1 | 1 | The incumbents are working in the SP&N Directorate. Their services will be available to assist the principal investigator, an additional duty along with his own sectional activities. Additional charge allowance will be paid from the project. |
| Junior clerk |  | 2 | The incumbents are working in the SP&N Directorate. Their services will be available to assist the principal investigator, an additional duty along with his own sectional activities. Additional charge allowance will be paid from the project. |

STAFF REQUIRE FOR THE PROJECT ACTIVITIES

| S# | Name of Posts | No. | Justification & responsibilities of the Manpower to be hired | Required Skill |
| --- | --- | --- | --- | --- |
| 1 | Research Officer (as per project policy) Duration: For the Project life. | 1 | One Research Officer will be hired for: - Identification and isolation of soil micro-organism for soil enhancement. - Formulation for isolated micro-organism for soil enhancer. - Bio-fertilizer development | A Research Officer will be hired having minimum qualification MS/M.Sc. (HONS) in Plant Pathology or Soil Science and at least twenty (20) years relevant experience in a university or public sector research organization in the field of agriculture (Plant Pathology or Soil Microbiology). He/she must have at least six research publications. He/she must have experience in isolation of soil microbes beneficial for crops of the Province and subsequent development of soil enhancer or bio-fertilizer. Minimum age limit will be 30 years. |
| 2 | Internee as per government policy notification vide No. SO(E)P&D/3-4/PIP/2018 | 5 | They will be responsible for conducting and designing of research trials and also carry out lab activities Research fellows will collect field and laboratory data to analyze and compile for report writing. They will also assist the SRO/ROs in field and lab activities. | M.Sc./B.Sc. (Hons) in Agri. |
| 3 | DPL @ Rs. 673 per day | 8 per month | They will perform the activities: - Preparation of land for field experiments and sowing of the project-based experiments. - Maintenance of field experiments eg: hoeing, weeding and thinning and irrigation - Application of fertilizer and pesticides - Assistance in sample collection of waste water used for irrigation purpose throughout the province - Processing of collected samples in the labs - Maintenance of labs i.e., cleaning of labs and glass wares and - Watch & ward | - Physical fit and healthy - Preferably literate having farming background |

Procurement Committee:

The Procurement/Purchase Committee comprising of following officers the department will be constituted at provincial level for bidding process and inspection of the firms; processing and quality assurance:

- Director Soil Plant & Nutrition        	Chairman

- Representative of DGAR (PRO/SRO)	Member

- Senior Research Officer (Pesticide Residue) DSPN	Member

- Senior Research Officer (Soil Chemistry) DSPN	Member

- Office Assistant/Senior Clerk      Secretary /Member

The terms of reference of the committee shall be as under:

- To draft bid/tender documents for the procurement process.

- To formulate scoring criteria of the bidders.

- To scrutinize and evaluate the technical as well as financial bids/tenders submitted by the participating firms as per bids/tenders documents viz a viz specifications of the items/equipment to be procured.

14.       Additional projects/decisions required

- Indicate additional projects/decisions required to optimize the investment being undertaken on the project

The Project Incharge would be the Drawing and Disbursement Officer of the Project.

15.	Certified that the project proposal has been prepared on the basis of 		instructions 	provided by the Planning Commission for the preparation 	of PC-I for production sector projects

________________________

| PREPARED BY: |  | Mr. Zia Ullah Director, Soil and Plant Nutrition, ARI Tarnab Peshawar |
| --- | --- | --- |
| CHECKED BY: |  | Dr. Bashir Ahmad Director Research Planning Directorate General, Agricultural Research, Peshawar |
| SUBMITTED BY: |  | __________________________ Dr. Abdul Rauf Director General Agricultural Research System Khyber Pakhtunkhwa, Peshawar |
| COUNTERSIGNED BY: |  | Dr. Muhammad Israr Secretary to Government of Khyber Pakhtunkhwa Agriculture, Livestock & Cooperation Department, Peshawar. |
| APPROVED BY: |  | PDWP Dated______________ |

ANNEXURES

Annexure-I

Exposure Visit

Detail of Expenditure incurred on Exposure Visit (04 days) for 10 participants

| S. No | Activity | Expenditure (Rs. Millions) |
| --- | --- | --- |
| 1 | Vehicle Hiring charges | 0.050 |
| 2 | POL Charges | 0.042 |
| 3 | Break Fast 300 * 10*4 | 0.012 |
| 4 | Refreshment 150*10*4 | 0.006 |
| 5 | Lunch 500*10*4 | 0.020 |
| 6 | Dinner 500*10*4 | 0.020 |
| 7 | Room Rent 3000 *5*3 | 0.045 |
| 8 | Banner, Stationary, Miscellaneous Charges | 0.025 |
|  | Total | 0.220 |

Annexure-II

Cost of One day Training for 25 Participants (farmers/scientists)* at ARI Tarnab

| S# | Particulars | Unit | Numbers | Unit cost (Rs) | Frequency | Amount (Million Rs.) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 5 resource persons | Persons | 5 | 0.005 | 1 | 0.025 |
| 2 | Training coordinator | Person | 1 | 0.005 | 1 | 0.005 |
| 3 | Training assistant | Person | 1 | 0.002 | 1 | 0.002 |
| 4 | Honoraria Rs.1000/-per day for 25 participants | Person | 25 | 0.001 | 1 | 0.025 |
| 5 | Two times tea with cookies and samosa etc. for 25 persons Rs200/- per participant | Person | 25 | 0.0002 | 1 | 0.005 |
| 6 | Lunch for 25 participants 500/-per participant | Person | 25 | 0.0005 | 1 | 0.013 |
| 7 | Stationery | L/S | 1 | 0.01 | 1 | 0.010 |
| 8 | Banflex 8X4 2 | Nos. | 1 | 0.003 | 1 | 0.003 |
| 9 | Miscellaneous | L/S | 1 | 0.005 | 1 | 0.005 |
|  | Total |  |  |  |  | 0.093 |

*farmers training = 04 Nos

* Staff training = 04 Nos

Annexure-III

UNIT COST FOR ONE DAY TRAINING FOR 25 PARTICIPANTS AT FARMER FIELD

| S. No | Particulars | Unit | Unit cost (Rs) | Numbers | Amount (Rs. M) |
| --- | --- | --- | --- | --- | --- |
| 1 | 5 resource persons | Persons | 5000 | 5 | 0.025 |
| 2 | Training coordinator | Person | 5000 | 1 | 0.005 |
| 3 | Training assistant | Person | 2000 | 1 | 0.002 |
| 4 | Honoraria @ Rs.1000/-per day for 25 participants | Person | 1000 | 25 | 0.025 |
| 5 | Transportation2 haices Rs.25000/-per haice per day |  | 25000 | 2 | 0.05 |
| 6 | Two times tea with cookies and samosa etc. for 25 persons Rs200/- per participant | Person | 200 | 25 | 0.005 |
| 7 | Lunch for 25 participants 500/-per participant | Person | 500 | 25 | 0.0125 |
| 8 | Stationery | L/S | 10000 | 1 | 0.01 |
| 9 | Banflex 8X4 2 | Nos. | 3000 | 1 | 0.003 |
| 10 | Miscellaneous | L/S | 5000 | 1 | 0.005 |
|  | Total |  |  |  | 0.143 |

Field Days = 05 Nos

Annexure-IV

List of Pesticide Standards

| S. No. | Pesticide Standard | Upper Case | Unit price (Million Rs.) |
| --- | --- | --- | --- |
| 1 | Dichlorovas | Dichlorovas | 0.055 |
| 2 | Lambda Cypermethrin | Lambda Cypermethrin | 0.044 |
| 3 | Chlorpyrifos | Chlorpyrifos | 0.055 |
| 4 | Cypermethrin | Cypermethrin | 0.033 |
| 5 | BromoxynilMcpa | BromoxynilMcpa | 0.044 |
| 6 | Acetamiprid | Acetamiprid | 0.033 |
| 7 | Thiophanate Methyl | Thiophanate Methyl | 0.055 |
| 8 | Flusilazole | Flusilazole | 0.033 |
| 9 | Triasulfuron | Triasulfuron | 0.044 |
| 10 | Fiperonil | Fiperonil | 0.033 |
| 11 | Nicosulfuron | Nicosulfuron | 0.055 |
| 12 | Bifinthrin | Bifinthrin | 0.044 |
| 13 | Glyphosate | Glyphosate | 0.055 |
| 14 | Fluroxypyrmephyl | FluroxypyrMephyl | 0.033 |
| 15 | Imidacloprid | Imidacloprid | 0.044 |
| 16 | Metribuzin | Metribuzin | 0.033 |
| 17 | Difenconazole | Difenconazole | 0.055 |
| 18 | Acetocholar | Acetocholar | 0.044 |
| 19 | Ddvp | Ddvp | 0.055 |
| 20 | Fenoxy-P-Ethyl | Fenoxy-P-Ethyl | 0.033 |
| 21 | Tebuconazole | Tebuconazole | 0.044 |
| 22 | Mesotrione | Mesotrione | 0.033 |
| 23 | Atrazine | Atrazine | 0.055 |
| 24 | Iprodion | Iprodion | 0.055 |
| 25 | Cyhalothrin | Cyhalothrin | 0.033 |
| 26 | Lambda-Cyhalothrin | Lambda-Cyhalothrin | 0.044 |
| 27 | Bromoxynil | Bromoxynil | 0.033 |
| 28 | Clothianidin | Clothianidin | 0.055 |
| 29 | Quizalofop-p-ethyl | Quizalofop-P-Ethyl | 0.044 |
| 30 | Ammonium Salt Glyphosate | Ammonium Salt Glyphosate | 0.055 |
| 31 | Propiconazole | Propiconazole | 0.033 |
| 32 | Bifenthrin | Bifenthrin | 0.044 |
| 33 | Pyridaben | Pyridaben | 0.033 |
| 34 | Ametryn | Ametryn | 0.055 |
| 35 | Myclobutanil | Myclobutanil | 0.055 |
| 36 | clodinafoppropargyl | ClodinafopPropargyl | 0.044 |
| 37 | Aluminum Phosphide | Aluminum Phosphide | 0.055 |
| 38 | Deltamethrin | Deltamethrin | 0.033 |
| 39 | Mesotrione Atrazine | Mesotrione Atrazine | 0.033 |
| 40 | Hexaconazole | Hexaconazole | 0.055 |
| 41 | Procymidone | Procymidone | 0.033 |
| 42 | Pendimethalin | Pendimethalin | 0.055 |
| 43 | Nitenpyram | Nitenpyram | 0.033 |
| 44 | Metiram | Metiram | 0.044 |
| 45 | Triazophos | Triazophos | 0.033 |
| 46 | Beta cyfluthrin | Beta Cyfluthrin | 0.055 |
| 47 | Pyroxsulam-Florasulam | Pyroxsulam-Florasulam | 0.044 |
| 48 | Metsulfuron Methyl | Metsulfuron Methyl | 0.055 |
| 49 | Trichlorfon | Trichlorfon | 0.033 |
| 50 | Carfentrazone-ethyl | Carfentrazone-Ethyl | 0.044 |
| 51 | Carbendazim | Carbendazim | 0.033 |
| 52 | Abamectin | Abamectin | 0.055 |
| 53 | Tricyclazole | Tricyclazole | 0.044 |
| 54 | Clopyralid | Clopyralid | 0.033 |
| 55 | Penconazole | Penconazole | 0.033 |
| 56 | Haloxyfop-R-Methyl | Haloxyfop-R-Methyl | 0.055 |
| 57 | Metalaxyl-Mancozeb | Metalaxyl-Mancozeb | 0.044 |
| 58 | Alpha Cypermethrin | Alpha Cypermethrin | 0.055 |
| 59 | Borax | Borax | 0.033 |
| 60 | Pymetrozine | Pymetrozine | 0.033 |
| 61 | Pyriproxyfen | Pyriproxyfen | 0.055 |
| 62 | flucarbazone-sodium | Flucarbazone-Sodium | 0.044 |
| 63 | Sulfosulfuron | Sulfosulfuron | 0.055 |
| 64 | Betacyfluthrin | Betacyfluthrin | 0.055 |
| 65 | clodinofoppropargyl | ClodinofopPropargyl | 0.044 |
| 66 | pyroxsulamflorasulam | PyroxsulamFlorasulam | 0.055 |
| 67 | nephthilacitic acid | NephthilAcitic Acid | 0.033 |
| 68 | Carfertrazone | Carfertrazone | 0.055 |
| 69 | Accelachler | Accelachler | 0.044 |
| 70 | Carbendazen | Carbendazen | 0.055 |
| 71 | Abamedtin | Abamedtin | 0.033 |
| 72 | Bromaxnil | Bromaxnil | 0.033 |
| 73 | Imdacloprid | Imdacloprid | 0.044 |
| 74 | Biostimulant | Biostimulant | 0.055 |
| 75 | fenoxaprop-p-ethyl | Fenoxaprop-P-Ethyl | 0.044 |
| 76 | MCPA | Mcpa | 0.033 |
| 77 | Acetochlor | Acetochlor | 0.055 |
| 78 | haloxyfop-R-Methyle | Haloxyfop-R-Methyle | 0.033 |
| 79 | metalaxyl-manco | Metalaxyl-Manco | 0.044 |
| 80 | fungicide+carbendazim | Fungicide+Carbendazim | 0.033 |
| 81 | Chloropyrifos | Chloropyrifos | 0.044 |
| 82 | Petroleum | Pertoleum | 0.055 |
| 83 | calcium bore | Calcium Bore | 0.044 |
| 84 | pymentrozine | Pymentrozine | 0.044 |
| 85 | Misotrione | Misotrione | 0.044 |
| 86 | fina-prop-methyal | Fina-Prop-Methyal | 0.055 |
| 87 | tria-oxydom | Tria-Oxydom | 0.044 |
| 88 | clodina-fop-propaigyal | Clodina-Fop-Propaigyal | 0.055 |
| 89 | flucarbazone sodium | Flucarbazone Sodium | 0.033 |
| 90 | Mandipropamid | Mandipropamid | 0.044 |
| 91 | Peopokeesdan | Peopokeesdan | 0.044 |
| 92 | ammounium salt of glyphosate | Ammounium salt of Glyphosate | 0.055 |
| 93 | azinphos-methyl | Azinphos-Methyl | 0.055 |
| 94 | azinphos-ethyl | Azinphos-Ethyl | 0.044 |
| 95 | Captan | Captan | 0.055 |
| 96 | Carbofuran | Carbofuran | 0.033 |
| 97 | Carbosulfan | Carbosulfan | 0.033 |
| 98 | Chlofenapyr | Chlofenapyr | 0.055 |
| 99 | Diafenthiuron | Diafenthiuron | 0.044 |
| 100 | Dieldrin | Dieldrin | 0.055 |
| 101 | Dimethoate | Dimethoate | 0.055 |
| 102 | endosulfan alpha | Endosulfan Alpha | 0.044 |
| 103 | endosulfan beta | Endosulfan Beta | 0.055 |
| 104 | endosulfan sulfate | Endosulfan Sulfate | 0.033 |
| 105 | Fenitrothion | Fenitrothion | 0.055 |
| 106 | Fenoxycarb | Fenoxycarb | 0.044 |
| 107 | Fenvalerate | Fenvalerate | 0.055 |
| 108 | Heptachlor | Heptachlor | 0.033 |
| 109 | Indoxacarb | Indoxacarb | 0.033 |
| 110 | lambda cyhalothrin | Lambda Cyhalothrin | 0.044 |
| 111 | Malathion | Malathion | 0.055 |
| 112 | methamidophos | Methamidophos | 0.044 |
| 113 | Methomyl | Methomyl | 0.033 |
| 114 | Methoxyfenozide | Methoxyfenozide | 0.055 |
| 115 | Mevinphos | Mevinphos | 0.033 |
| 116 | 4,4-DDT | 4,4-Ddt | 0.044 |
| 117 | Parathion-ethyl | Parathion-Ethyl | 0.033 |
| 118 | Parathion-methyl | Parathion-Methyl | 0.044 |
| 119 | Pirimicarb | Pirimicarb | 0.055 |
| 120 | Pirimiphos-ethyl | Pirimiphos-Ethyl | 0.044 |
| 121 | 2,4-DDT | 2,4-Ddt | 0.044 |
| 122 | Propargite | Propargite | 0.044 |
| 123 | Spinosed | Spinosed | 0.055 |
| 124 | Triachlorfon | Triachlorfon | 0.044 |
| 125 | Aldicarb | Aldicarb | 0.055 |
| 126 | Acephate | Acephate | 0.033 |
| 127 | sigma HCH | Sigma Hch | 0.044 |
| 128 | TCP (3,5,6-Trichloro-2-pyridinol) | Tcp (3,5,6-Trichloro-2-Pyridinol) | 0.044 |
| 129 | s-metolachlor | S-Metolachlor | 0.055 |
| 130 | Thiamethoxam | Thiamethoxam | 0.055 |
| 131 | Emamectin Benzoate | Emamectin Benzoate | 0.033 |
| 132 | Clodinafappropargyl | ClodinafapPropargyl | 0.044 |
| 133 | Azoxystrobin | Azoxystrobin | 0.044 |
| 134 | Lufenuron | Lufenuron | 0.055 |
| 135 | Micronutrient Standards | Zn, Fe, Cu, Mn (Rs. 0.025/unit) | 0.22 |
| 136 | Heavy Metal Standards | Cd, Ni, Pb, Cr (Rs.0.025/unit) | 0.22 |
|  | Total |  | 6.435 |

Annexure-V

Laboratory Chemicals

| S. No. | Name of Item | Grade | Amount/ Unit | Required Amount | Price/Unit (M.Rs.) | Total Price (M.Rs.) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Acetic Acid Glacial 100% | Merck | 2.5 Ltr | 6 Bottles | 0.027 | 0.163 |
| 2 | Acetone | Merck | 2.5 Ltr | 12Bottles | 0.033 | 0.39 |
| 3 | Acetonitrile Hypergrade for LC-MS Lichrosolv | Merck | 2.5 Ltr | 12Bottles | 0.05 | 0.6 |
| 4 | Acetonitrile 99.9% | Daejung | 4 Ltr | 12 Bottles | 0.014 | 0.334 |
| 5 | Charcoal Activated Extra Pure | - | KG | 03 KG | 0.022 | 0.065 |
| 6 | Cyclohexane | Merck | 2.5 Ltr | 03 Bottles | 0.011 | 0.034 |
| 7 | Di-Chloromethane (Methylene Chloride) | 0.99 | 2.5 Ltr | 03 Bottles | 0.009 | 0.027 |
| 8 | Di-Sodium Hydrogen Citrate 1, 5-Hydrate | 99+% | 500gm | 03 KG | 0.022 | 0.067 |
| 9 | EDTA Powder |  | KG | 03 KG | 0.01 | 0.029 |
| 10 | Ethanol (Ethyl Alcohol) 95-97% | 95-97% | 2.5 Ltr | 12 Bottles | 0.004 | 0.05 |
| 11 | Ethanol Absolute 99.9% | HPLC | 2.5 Ltr | 12 Bottles | 0.019 | 0.228 |
| 12 | Ethyl Acetate 99.5% | 0.995 | 2.5 Ltr | 10 Bottles | 0.009 | 0.089 |
| 13 | Formic Acid | - | 2.5Ltr | 03 Bottles | 0.01 | 0.029 |
| 14 | Iso-Octane (2,2,4-Trimethylpentane) | 0.995 | 2.5 Ltr | 6 Bottles | 0.032 | 0.19 |
| 15 | Alumina | Extration Grade | KG | 03 KG | 0.009 | 0.027 |
| 16 | Methanol 99.9% | 0.999 | 2.5 Ltr | 12 Bottles | 0.003 | 0.038 |
| 17 | N-Hexane for HPLC | LiChrosolv | 2.5 Ltr | 12 Bottles | 0.027 | 0.32 |
| 18 | N-Hexane for GC (For residue analysis) | SupraSolv | 2.5 Ltr | 12 Bottles | 0.052 | 0.624 |
| 19 | Petroleum Spirit 40-60 C GR for analysis | EMSURE | 2.5 Ltr | 1 Bottles | 0.012 | 0.012 |
| 20 | Sodium Acetate Anhydrous Gr for Analysis | Sigma Aldrich EMSURE | KG | 03 KG | 0.016 | 0.049 |
| 21 | Sodium Acetate Trihydrate Gr for Analysis | Sigma Aldrich GR | KG | 03 KG | 0.011 | 0.033 |
| 22 | Sodium Chloride for Analysis Acs, Iso, reag, PhEur | Sigma Aldrich 99.5% | KG | 03 KG | 0.004 | 0.012 |
| 23 | Sodium Sulfate Anhydrous Extra Pure | Extra Pure | KG | 03 Bottles | 0.025 | 0.075 |
| 24 | Magnesium Sulphate Anhydrous | Daejung | KG | 6 Bottles | 0.038 | 0.225 |
| 25 | Florisil | Sigma Aldrich | 500 gm | 3 Bottles | 0.041 | 0.123 |
| 26 | Glass-wool | Sigma Aldrich | 50 g | 5 Bottles | 0.014 | 0.068 |
| 27 | Propanediol | Sigma Aldrich | 2.5 Ltr | 3 Bottles | 0.01 | 0.031 |
| 28 | Trisodium Citrate Dihydrate | Sigma Aldrich | KG | 03 Bottles | 0.014 | 0.042 |
| 29 | Disodium Hydrogen Citrate Sesquihydrate | Sigma Aldrich | KG | 03 Bottles | 0.015 | 0.044 |
| 30 | PSA SPE Bulk Packing | Extra Pure | 100g | 02 Bottles | 0.078 | 0.157 |
| 31 | C18 | Grade I, ?98.5% | 100g | 02 Bottles | 0.068 | 0.136 |
| 32 | Toluene | Merck | 2.5 Ltr | 02 Bottles | 0.016 | 0.033 |
| 33 | Sodium Nitrite | 0.994 | KG | 02 KG | 0.014 | 0.028 |
| 34 | Potassium Dihydrogen phosphate GR For Analysis | >99.5% | KG | 03 KG | 0.01 | 0.029 |
| 35 | Sodium Hydroxide Pellets Reagent Grade 99% | 0.99 | KG | 15 KG | 0.005 | 0.068 |
| 36 | Ammonium Iron 9Li) SulphateHexahydrate (Mohr's Salt) | NORMAPUR | KG | 02 KG | 0.015 | 0.029 |
| 37 | Iron (li) Sulphatehexahydrate Analar | AR | KG | 02 KG | 0.01 | 0.02 |
| 38 | Mercury (li) Sulphate | LAB | 250 gm | 01 KG | 0.022 | 0.086 |
| 39 | Potassium Hydrogen Phthalate Gr for Analysis | 0.995 | 250 gm | 01 KG | 0.012 | 0.049 |
| 40 | Silver Sulphate Purified Analysis Acs | PURIFIED | 25 gm | 01 KG | 0.021 | 0.831 |
| 41 | Potassium Dichromate 99.0+% | RECTAPUR/ MERCK | KG | 03 KG | 0.016 | 0.049 |
| 42 | Ferrion Indicator Solution for Waste Water Analysis | - | 100 ml | 02 Bottles | 0.012 | 0.024 |
| 43 | Potassium chromate Acs,Reag. PhEur | EMSURE | Kg | 01 KG | 0.025 | 0.025 |
| 44 | Silver Nitrate Meets Analytical Specification of PH. Eur.Bp | 99.8+% | 100gm | 500 gm | 0.047 | 0.234 |
| 45 | Phenolphthalein Indicator Acs | Indicator | 100gm | 200 gm | 0.01 | 0.019 |
| 46 | Mehthl Orange Indicator | Indicator | 25gm | 50 gm | 0.005 | 0.009 |
| 47 | Sodium carbonate Anhydrous for Analysis | EMSURE | Kg | 02 KG | 0.009 | 0.018 |
| 48 | Sulphuric Acid | AR | 2.5Ltr | 12 Bottles | 0.016 | 0.198 |
| 49 | Bromocresol green indicator | Indicator | 5gm | 10 gm | 0.006 | 0.012 |
| 50 | Ammonium Choride | EMSURE | 500gm | 01 KG | 0.005 | 0.009 |
| 51 | Ammonia Solution32% (Ammoonium Hydroxide) | 0.32 | 2.5ltr | 01 Bottles | 0.011 | 0.011 |
| 52 | Erochrome Black T | Indicator | 25gm | 50 gm | 0.005 | 0.01 |
| 53 | Murexide (Ammonium Purpurate) | - | 10gm | 20 gm | 0.008 | 0.015 |
| 54 | Magnesium chloride Hexahydrate for Molecular Biology | Molecular Bi | 500gm | 01 KG | 0.01 | 0.019 |
| 55 | Potassium Nitrate GR for analysis | EMSURE | Kg | 02 Kg | 0.013 | 0.025 |
| 56 | Barium Chloride GR for analysis | GR | Kg | 02 KG | 0.01 | 0.02 |
| 57 | Hydrochloric acid 37% | Extra Pure | 2.5Ltr | 6 Bottles | 0.014 | 0.084 |
| 58 | Ortho Posphoric acid 85%, acs, islo,reag. Pheur for analy | EMSURE | 2.5Ltr | 01 Bottles | 0.016 | 0.016 |
| 59 | Sulphanilamide Analar | AR | 100gm | 200 gm | 0.016 | 0.031 |
| 60 | N-(1-naphthyl) EthylenediamDihydrochloride GR for Analysis | GR | 5gm | 10 gm | 0.013 | 0.025 |
| 61 | Di-Sodium Oxalater FR for analysis | EMSURE | Kg | 01 KG | 0.04 | 0.04 |
| 62 | Dpph free Radical (2,2-Diphenyl-1- Picrylhydrazyl) | Biochemical | 50mg | 100 mg | 0.022 | 0.043 |
| 63 | Postassium Antimony Tartrate | - | 250mg | 500 mg | 0.013 | 0.026 |
| 64 | Ammonium MalybadateTetrahydrate | Extra Pure | 250mg | 500 mg | 0.019 | 0.038 |
| 65 | Ascorbic Acid for analysis | EMSURE | 100mg | 03 KG | 0.009 | 0.259 |
| 66 | Postassium Dihydrogen Phosphate GR for Analysis | >99.5% | Kg | 01 KG | 0.01 | 0.01 |
| 67 | Ammonium Peroxodisulphate GR for Analysis | GR | Kg | 01 Kg | 0.011 | 0.011 |
| 68 | Hydrazine Sulphate 99+% | ACS | 100gm | 200 gm | 0.022 | 0.043 |
| 69 | Hhexamethyleneteramine (Hexamine) 99% | 0.99 | Kg | 01 KG | 0.015 | 0.015 |
| 70 | Ferrous Ammonium Sulphate (FAS) | - | Kg | 02 KG | 0.014 | 0.028 |
| 71 | Ferroin Indicator | - | 100ml | 200 ml | 0.012 | 0.024 |
| 72 | 1,10 phenanthroline monohydrate | - | 10g | 20 gm | 0.015 | 0.029 |
| 73 | potassium Hydrogen Pthalatek HP | - | 500g | 01 KG | 0.015 | 0.029 |
| 74 | Ferrous Chloride FeCl3.6H2O | - | 500g | 01 KG | 0.009 | 0.018 |
| 75 | Iron (III) oxide | - | 500g | 01 KG | 0.008 | 0.016 |
| 76 | Sodium borohydride | - | 100g | 200 gm | 0.016 | 0.031 |
| 77 | Ammonium Sulfate | - | Kg | 02 KG | 0.011 | 0.023 |
| 78 | QuEChERS Dispersive 15ml, All food type, AOAC,w/CH 50/PK (General fruits and vegetables without Charcoal) | - | 50/kit | 25 Kits | 0.056 | 1.394 |
| 79 | QuEChERS Dispersive 15ml, pigmented fruits and vegetables, AOAC,w/CH 50/PK | - | 50/kit | 25 Kits | 0.056 | 1.394 |
| 80 | QuEChERS Dispersive 15ml, highly pigmented fruits and vegetables, AOAC,w/CH 50/PK | - | 50/kit | 15 Kits | 0.056 | 0.837 |
| 81 | Potassium Hydroxide | - |  | 2 KG | 0.04 | 0.08 |
| 82 | Nitric Acid HNO3 | - |  | 3 Bottles | 0.004 | 0.011 |
| 83 | Perchloric Acid | - |  | 2 Bottle | 0.02 | 0.04 |
| 84 | Sodium Hydroxide Pellets | Extra Pure |  | 6 Kg | 0.003 | 0.018 |
| 85 | FerriusSulphate | AR |  | 3 KG | 0.005 | 0.015 |
| 86 | Ascarbic Acid | AR |  | 3 Kg | 0.004 | 0.011 |
| 87 | CupparSulphate | - |  | 2 Kg | 0.004 | 0.008 |
| 88 | Potassium Sulphate | - |  | 3 Kg | 0.005 | 0.015 |
| 89 | Sodium Carbonate | - |  | 3 Kg | 0.005 | 0.015 |
| 90 | Sodium Bi Carbonate | - |  | 2 Kg | 0.003 | 0.005 |
| 91 | Ammoium Hydrogen Carbonate | - |  | 2 KG | 0.004 | 0.008 |
| 92 | Zinc Sulphate | - |  | 3 KG | 0.004 | 0.012 |
| 93 | Zinc Metal | - |  | 3 Kg | 0.004 | 0.012 |
| 94 | Potassium Antimany Tartarate | - |  | 1 Kg | 0.027 | 0.027 |
| 95 | DTPA | - |  | 2 KG | 0.005 | 0.01 |
| 96 | Potassium Chloride | - |  | 3 Kg | 0.004 | 0.012 |
| 97 | Hydrocholric acid amule |  |  | 4 No. | 0.003 | 0.012 |
| 98 | Methyal Orange Indicator | Indicator |  | 25 gm | 0.005 | 0.005 |
| 99 | Methyal Blue Indicator | Indicator |  | 25 gm | 0.005 | 0.005 |
| 100 | Methyal Red Indicator | Indicator |  | 25 gm | 0.005 | 0.005 |
| 101 | Bromocresole Green | Indicator |  | 100 gm | 0.01 | 0.01 |
| 102 | Erecrome Black T | Indicator |  | 100 gm | 0.008 | 0.008 |
| 103 | Azomethan | Lab Grade |  | 25 gm | 0.025 | 0.025 |
| 104 | Potassium Permanganate | ACS reagent, ?99.0% | KG | 2 KG | 0.027 | 0.054 |
|  | Total |  |  |  |  | 11.068 |

Annexure-VI

List of IT Equipment

| S. No. | Description of Equipment | Quantity | Unit Price (Million Rs.) | Total Price (Rs. Millions) |
| --- | --- | --- | --- | --- |
| 1 | Multimedia/Projector (1920 x 1200) | 1 | 0.700 | 0.700 |
| 2 | Laser jet 3 in 1 Printer (photocopier, scanner & printer) | 1 | 0.250 | 0.250 |
| 3 | Laptops (10th Generation, 8GB RAM, 1TB Hard drive) | 4 | 0.200 | 0.800 |
| 4 | Laser jet Printer (Colored) | 1 | 0.160 | 0.160 |
| 5 | Computer system (3rd Generation,5 GB RAM and 500GB Hard Drive): (With LCDs, Mouse, keyboards) | 4 | 0.120 | 0.480 |
| 6 | Laser jet Printer (Black) | 5 | 0.083 | 0.415 |
|  | Total |  |  | 2.805 |

Annexure-VII

Laboratory Equipment

| S. No | Equipment Specifications | Qty | Unit Price | (Million Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Grinding Mill | 1 | 0.400 | 0.400 |
| 2 | Concentrator Nitrogen Jet Assembly | 1 | 1.600 | 1.600 |
| 3 | Safety Cabinets (Chemical Resistance, for Storage of Flammable and Toxic Chemicals) | 1 | 1.500 | 1.500 |
| 4 | Shaker (Flask/Test tube Wrist Shaker) | 1 | 0.200 | 0.200 |
| 5 | Shaker (Reciprocating Shaker) Bench Top | 1 | 0.500 | 0.500 |
| 6 | Lab Environment Monitoring Devices: Digital Thermometers, Digital Thermohygrometer with Dew Point and Alarm, Smoke Detector, Electricity Fluctuation meter and other Items as per requirement for Accreditation (Lumsum) | 2 | 0.500 | 1.000 |
| 7 | Fume hoods, Blower/Exhaust System for Labs | 3 | 2.000 | 6.000 |
| 8 | Tool kits for lab and Field Activities | 2 | 0.710 | 1.420 |
| 9 | Personal Protection/Safety Equipment i.e Eye Wash Unit, Fire Extinguisher, first Aid box, Masks, Gloves, Goggles etc. Lumsum as per requirement | 2 | 0.500 | 1.000 |
| 10 | Blender/Mixture for Laboratory (Small Size) | 2 | 0.400 | 0.800 |
| 11 | Solvent Fraction Distillation Assembly/Unit: Comprising of Distillation Column, Fractionating Column and other essential parts/accessories. | 1 | 0.700 | 0.700 |
| 12 | LC/MS/MS (Pesticide analyzer) triple quadruple with quaternary pump, DAD detector, 100 vials auto sampler, 6 LC/MS/MS column of different phase for the application of pesticide residue analysis, recommended consumables for LC/MS/MS operation, Nitrogen generator 32 L/Min, Stabilizer, UPS, Lates PC, LCD, Laser Printer, etc. (On plug and play basis) | 1 | 50.000 | 50.000 |
| 13 | Nitrogen Generator | 1 | 2.000 | 2.000 |
| 14 | High performance liquid chromatography (HPLC with Diode array and fluorescence Detector Quaternary pump, degasser, Auto-sampler, Automatic column switching values, software and accessories 6 LC columns of different Phase and Dimensions with latest PC, LCD, Laser Printer, UPS, Stabilizers (with plug and play basis), oven system with movable trolley | 1 | 20.000 | 20.000 |
| 15 | Solid Phase Extraction manifold | 1 | 1.200 | 1.200 |
| 16 | -86? ULT Freezer (Standing) | 2 | 2.000 | 4.000 |
| 17 | Water bath | 1 | 0.400 | 0.400 |
| 18 | Rapid field pesticide residue test kits | 100 | 0.010 | 1.000 |
| 19 | Lab Trolley with Wheels | 4 | 0.160 | 0.640 |
| 20 |  |  |  |  |
| 21 | Microwave Digester (Digestion upto 12 samples in less than 20mints with turbo heating, reaction control and turbo cooling system) | 1 | 3.500 | 3.500 |
| 22 | Soil Dispersion Machine (Three Spindal Model, 115/60 Volts/htz) | 2 | 0.350 | 0.700 |
| 23 | Hydrometer | 8 | 0.025 | 0.200 |
| 24 | ICP Inductively Coupled Plasma Mass Spectrometer or optical emission spectroscopy, 9-digit dynamic range electron multiple detector, Mass Range5 to 260, collision cell lens system, Eco Mode (5 L/min of Plasma) Argon flow-8-20 L/Min Plasma Shear-18-25L/Min.Spectral range 165-900nm with resolution less .009 etc. | 1 | 21.000 | 21.000 |
| 25 | Flame Photometer 300 measurements per hour, Display: TFT-Display with integrated 8,4" TFT touch screen, 800x600 Pixel, measurement range: 0.1-4500 ppm, Detection : 0.01-0.03 ppm, Precision: 0.2 % at 40 ppm, Accuracy: 1 % at 40 ppm, Aspiration rate: <6mL/min, Fuel supply: both L.P.G and Natural gas, .Accessories: 24 character plain paper printer etc. | 2 | 1.500 | 3.000 |
| 26 | Spectrophotometer Double Beam, Model: UV-1800 UV-VIS Spectrophotometer, wavelength 190 to 1100nm, spectral band width 1nm (190 to 1100nm), Absorbance: -4 to 4 Abs, Transmittance: 0% to 400%, Photometric system: Double Beam, Wavelength setting: 0.1-nm increments, Wavelength repeatability: ±0.1nm, Wavelength accuracy: ±0.1nm at 656.1nm D2 ±0.3nm (190 to 1100nm), memory: USB memory (option) Saved as text and UVPC file etc | 2 | 1.800 | 3.600 |
| 27 | Digital pH meter for Lab use, | 4 | 0.200 | 0.800 |
| 28 | Digital EC meter for Lab use, | 4 | 0.400 | 1.600 |
| 29 | Analytical Balance Accuracy 0.1mg Weighing Scale Specs, Capacity (Kg): 0.32 Kg. Other Feathers: Backlit LCD Auw Only, Below Weigh Hook For Hanging Measurement, Choice Of Fully Calibrations | 1 | 0.500 | 0.500 |
| 30 | Top loader, capacity 6200 gm, accuracy: 0.01 gm, pan size: 170 x 180 (mm). | 1 | 0.400 | 0.400 |
| 31 | Hot Plate | 2 | 0.150 | 0.300 |
| 32 | Electric /Horizontal Shaker | 2 | 0.250 | 0.500 |
| 33 | Furnace Max. Temperature: 1800 °C, Working Temperature: 1700°C, Heating Element: Molybdenum Silicide | 1 | 0.650 | 0.650 |
| 34 | Oven Capacity 1000 liters, Temp. range 40-250 0C, Number of Shelves 05, Shelves Position 11, Stainless steel Chamber, Microprocessor digital control safety overheat thermostat | 1 | 0.500 | 0.500 |
| 35 | Kjeldhal Apparatus | 2 | 0.987 | 1.974 |
| 36 | Automatic Burette | 4 | 0.100 | 0.400 |
| 37 | Top Bottle Dispenser | 8 | 0.080 | 0.640 |
| 38 | Drying Cabinet Approx Capacity (litre): 1000, Internal dims (H x W x D cm): 138 x 116 x 62, External dims (H x W x D cm): 168 x 118 x 65 , No. of shelves: 3, Maximum temperature 50°C above ambient, Thermostat control for set temperature, Fan circulation on 500 & 1000 litre. | 1 | 1.600 | 1.600 |
|  | Total Rs. (Million) |  |  | 136.224 |

Annexure VIII

Vehicles

| S. No. | Particulars |  | Specification | Nos. | Total M (Rs) |
| --- | --- | --- | --- | --- | --- |
| 1 | Toyota Hilux |  | Single Cabin | 1 | 6.000 |
|  |  |  | 4x4 S/c Standard |  |  |
|  |  |  | model Latest |  |  |
|  |  |  | Diesel Fuel |  |  |
|  |  |  | Manual Transmission |  |  |
|  |  |  | 2800 cc Engine |  |  |
| 2 | Toyota Hilux |  | Single Cabin | 1 | 4.500 |
|  |  |  | 4x2 S/c Standard |  |  |
|  |  |  | model Latest |  |  |
|  |  |  | Diesel Fuel |  |  |
|  |  |  | Manual Transmission |  |  |
|  |  |  | 2494 cc Engine |  |  |
| 3 |  | Conversion charges | From single cabin to double cabin | 2 | 2.600 |
|  |  | G. Total |  |  | 13.100 |

Annexure-IX

List of Furniture

| S. No. | Particulars | Nos. | Estimated cost (Rs Million) |
| --- | --- | --- | --- |
| 1 | Executive table | 1 | 0.050 |
| 2 | Executive chairs | 1 | 0.040 |
| 3 | Office tables | 10 | 0.300 |
| 4 | Office chairs | 80 | 0.500 |
| 5 | Revolving chairs | 10 | 0.300 |
| 6 | Computer tables | 4 | 0.100 |
| 7 | Computer chairs | 4 | 0.050 |
| 8 | Wooden almirahs | 8 | 0.400 |
| 9 | File racks | 8 | 0.065 |
| 10 | Sofa set and one set Centre table | 2 | 0.250 |
|  | Total |  | 2.055 |

Annexure-X

Laboratory Glassware

| S. No. | Glassware Specification | Description | Qty | Unit cost (M.Rs) | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Pipette Glass Graduated 01 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0008 | 0.08 |
| 2 | Pipette Glass Graduated 05 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0007 | 0.07 |
| 3 | Pipette Glass Graduated 10 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0008 | 0.08 |
| 4 | Pipette Glass 01 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0008 | 0.08 |
| 5 | Pipette Glass 20 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0009 | 0.09 |
| 6 | Pipette Glass 30 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0009 | 0.09 |
| 7 | Pipette filer (Pi-pump plastic) 25ml | Laboratory Grade, Germany | 100 | 0.00104 | 0.14 |
| 8 | Graduated Glass Cylinders 10 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.000754 | 0.0754 |
| 9 | Graduated Glass Cylinders 25 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.000618 | 0.0618 |
| 10 | Graduated Glass Cylinders 50 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.000728 | 0.0728 |
| 11 | Graduated Glass Cylinders 100 ml without Cap | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.000728 | 0.0728 |
| 12 | Graduated Glass Cylinders 100 ml with Cap | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.000728 | 0.0728 |
| 13 | Glass funnels 3" (75mm) Short Stem Heavy Wall ACC to ISO 450mm | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00039 | 0.039 |
| 14 | Pateur Pipettes Glass 150 mm | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.0009 | 0.09 |
| 15 | Pateur Pipettes Rubber Bulb/Teats 01 ml | Rubber/Pollymer/Laboratory | 100 | 0.0006 | 0.06 |
| 16 | Glass pipettes stand | Chrom Coated or Equivalent | 10 | 0.00585 | 0.0585 |
| 17 | Graduated Suckers For Glass Pipette | Vitlab-Germany or Equivalent | 10 | 0.0065 | 0.065 |
| 18 | Separating Funnels (Glass) 100 ml | Pyrex Class A, ISO-Standards with batch certificate | 4 | 0.00325 | 0.013 |
| 19 | Separating Funnels (Glass) 250 ml | Pyrex Class A, ISO-Standards with batch certificate | 2 | 0.00403 | 0.00806 |
| 20 | Separating Funnels (Glass) 1000 ml | Pyrex Class A, ISO-Standards with batch certificate | 2 | 0.00507 | 0.01014 |
| 21 | Funnels (Glass) | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.001 | 0.1 |
| 22 | Buchner Funnel, 90 mm, porcelain | - | 50 | 0.00507 | 0.2535 |
| 23 | Laboratory Tripod stand | - | 10 | 0.00507 | 0.0507 |
| 24 | Volumetric Flask 1 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00507 | 0.507 |
| 25 | Volumetric Flask 2 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 26 | Volumetric Flask 5 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 27 | Volumetric Flask 10 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 28 | Volumetric Flask 25 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 29 | Volumetric Flask 50 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 30 | Volumetric Flask 100 ml | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.57 |
| 31 | Volumetric Flask 500 ml | Pyrex Class A, ISO-Standards with batch certificate | 25 | 0.00057 | 0.01425 |
| 32 | Volumetric Flask 1000 ml | Pyrex Class A, ISO-Standards with batch certificate | 25 | 0.00057 | 0.01425 |
| 33 | Round Bottom Flask 10 ml (29/32) | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 34 | Round Bottom Flask 25 ml (29/32) | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 35 | Round Bottom Flask 50 ml (29/32) | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 36 | Round Bottom Flask 100 ml (29/32) | Pyrex Class A, ISO-Standards with batch certificate | 100 | 0.00057 | 0.057 |
| 37 | Recovery Flask 500 ml | Pyrex Class A, ISO-Standards with batch certificate | 10 | 0.00057 | 0.0057 |
| 38 | Conical Flask with Caps 100 ml | Pyrex Class A, ISO-Standards with batch certificate | 50 | 0.00057 | 0.0285 |
| 39 | Conical Flask with Caps 250 ml | Pyrex Class A, ISO-Standards with batch certificate | 10 | 0.00057 | 0.0057 |
| 40 | Conical Flask with Caps 500 ml | Pyrex Class A, ISO-Standards with batch certificate | 25 | 0.00057 | 0.01425 |
| 41 | Conical Flask Without Caps 500ml | Pyrex Class A, ISO-Standards with batch certificate | 10 | 0.00057 | 0.0057 |
| 42 | Beaker 30 ml | Pyrex Class A, ISO-Standards with batch certificate | 50 | 0.00057 | 0.0285 |
| 43 | Beaker 50 ml | Pyrex Class A, ISO-Standards with batch certificate | 50 | 0.00057 | 0.0285 |
| 44 | Beaker 100 ml | Pyrex Class A, ISO-Standards with batch certificate | 25 | 0.00057 | 0.01425 |
| 45 | Beaker 250 ml | Pyrex Class A, ISO-Standards with batch certificate | 25 | 0.00057 | 0.01425 |
| 46 | Beaker 500 ml | Pyrex Class A, ISO-Standards with batch certificate | 10 | 0.00057 | 0.0057 |
| 47 | Beaker 1000 ml | Pyrex Class A, ISO-Standards with batch certificate | 10 | 0.00057 | 0.0057 |
| 48 | Micro-Pipettes Tips 0.1-10µl | Eppendorf or Equivalent Quality | 10 Packets (1000/PK) | 0.00507 | 0.0507 |
| 49 | Micro-Pipettes Tips 10-100µl | Eppendorf or Equivalent Quality | 10Packets (1000/PK) | 0.00507 | 0.0507 |
| 50 | Micro-Pipettes Tips 100-1000µl | Eppendorf or Equivalent Quality | 10 Packets (1000/PK) | 0.00507 | 0.0507 |
| 51 | Micro-Pipettes Tips 5 ml | Eppendorf or Equivalent Quality | 5 Packets (1000/PK) | 0.00507 | 0.02535 |
| 52 | Micro-Filters 0.2 µm | Eppendorf or Equivalent Quality (Nylon) | 5 Packets (1000/PK) | 0.00507 | 0.02535 |
| 53 | Micro Filters 0.25 µm | Eppendorf or Equivalent Quality (Nylon) | 5 Packets (1000/PK) | 0.00507 | 0.02535 |
| 54 | Micro Filters 0.45 µm | Eppendorf or Equivalent Quality (PTFE) | 5 Packets (1000/PK) | 0.00507 | 0.02535 |
| 55 | Paper Filter (Round) 0.2 µm for Syringe | Millipore HVLP04700 (Ireland) | 10 Packets | 0.00057 | 0.0114 |
| 56 | Paper Filter (Round) 0.45 µm HV for Syringe | Millipore HVLP01300 (Ireland) | 10 Packets | 0.00057 | 0.0114 |
| 57 | Glass vial 1ml with caps and septa | - | 50 Packets | 0.00057 | 0.0114 |
| 58 | Glass vial 2 ml with caps and septa | - | 50 Packets | 0.00057 | 0.0114 |
| 59 | Glass Vial 4 ml with caps and septa | - | 10 Packets | 0.00057 | 0.0057 |
| 60 | Glass Vial 5 ml with caps and septa | - | 10 Packets | 0.00057 | 0.0057 |
| 61 | Glass Vial Insert | - | 10 Packets | 0.009 | 0.09 |
| 62 | Vial Racks for 1 ml | Plastic | 10 Packets | 0.09 | 0.09 |
| 63 | Vial Racks for 2 ml | Plastic | 10 Packets | 0.09 | 0.09 |
| 64 | Vial Racks for 5 ml | Plastic | 10 Packets | 0.09 | 0.09 |
| 65 | Vial Racks for 10 ml | Plastic | 10Packets | 0.09 | 0.09 |
| 66 | Vial Racks for 25 ml | Plastic | 10 Packets | 0.09 | 0.09 |
| 67 | Eppendorf Tubes 1 ml | Eppendorf or Equivalent Quality | 10 Pkt (100/PK) | 0.009 | 0.09 |
| 68 | Eppendorf Tubes 2 ml | Eppendorf or Equivalent Quality | 11 Pkt (100/PK) | 0.09 | 0.09 |
| 69 | Eppendorf Tubes 5 ml | Eppendorf or Equivalent Quality | 12 Pkt (100/PK) | 0.09 | 0.09 |
| 70 | Conical Tubes (Falcon Tubes) Polypropylene 15 ml | Germany or Equivalent | 13 Pkt (100/PK) | 0.09 | 0.09 |
| 71 | Conical Tube Plastic with Cap 50 ml | Germany or Equivalent | 14 Pkt (100/PK) | 0.09 | 0.09 |
| 72 | Burette 50 ml Class A, with Glass Stopcock | Lab Glass Sp | 10 | 0.09 | 0.09 |
| 73 | Burette 100 ml Class A, with Glass Stopcock | Lab Glass Sp | 10 | 0.00507 | 0.0507 |
| 74 | Reflux Flask s 250 ml with 24/29 neck 30cm jacket | Germany | 2 | 0.00507 | 0.01014 |
| 75 | Reagent Bottle, Media/Storage Bottles, Graduated with Blue Crew Cap 100 ml | Pyrex Class A, ISO-Standards with batch certificate | 5 | 0.00507 | 0.02535 |
| 76 | Reagent Bottle, Media/Storage Bottles, Graduated with Blue Crew Cap 250 ml | Pyrex Class A, ISO-Standards with batch certificate | 5 | 0.00507 | 0.02535 |
| 77 | Reagent Bottle, Media/Storage Bottles, Graduated with Blue Crew Cap 500 ml | Pyrex Class A, ISO-Standards with batch certificate | 5 | 0.00507 | 0.02535 |
| 78 | Reagent Bottle, Media/Storage Bottles, Graduated with Blue Crew Cap 1000 ml | Pyrex Class A, ISO-Standards with batch certificate | 5 | 0.00507 | 0.02535 |
| 79 | Watch Glass with different sizes | Pyrex Class A, ISO-Standards with batch certificate | 50 | 0.00507 | 0.2535 |
| 80 | Deluxe Spatula 8" | All Stainless German Grade (9531S) | 5 | 0.00507 | 0.02535 |
| 81 | Agathe-SE Spatula | German Grade (9811S) | 5 | 0.00057 | 0.00285 |
| 83 | Cement Spatula #7 | German Grade (9802S) | 5 | 0.00057 | 0.00285 |
| 84 | Cement Spatula #22 | German Grade (9803S) | 5 | 0.00057 | 0.00285 |
| 85 | Cement Spatula #24 | German Grade (9804S) | 5 | 0.00057 | 0.00285 |
| 86 | Deluxe Spatula | German Grade (9810S) | 5 | 0.00057 | 0.00285 |
| 87 | Cement Spatula | German Grade (B225S) | 5 | 0.00057 | 0.00285 |
| 88 | Cement Spatula Flexible | German Grade (B225AS) | 5 | 0.00057 | 0.00285 |
| 89 | Laboratory Spatula #2R, Flexible | German Grade (9525S) | 5 | 0.00057 | 0.00285 |
| 90 | China Dishes | - | 25 | 0.00057 | 0.01425 |
| 91 | Reagent Bottle Dispensing Pump | - | 25 | 0.0057 | 0.1425 |
| 92 | Distilled Water Wash Bottle (10-100ml) | - | 50 | 0.00507 | 0.2535 |
| 93 | Laboratory Grade Metal ware Set - Support Stand (8" x 5"), 12mm Dia. Rod (24" L) | - | 10 | 0.00507 | 0.0507 |
| 94 | Stands for 15 ml Falcon tubes | - | 10 | 0.00507 | 0.0507 |
| 95 | Stands for 50 ml Falcon tubes | - | 10 | 0.00507 | 0.0507 |
| 96 | Sampling bags (Zipper bags) 500g capacity | - | 10 KGs | 0.00007 | 0.0007 |
| 97 | Sampling bags (Zipper bags) 1000g capacity | - | 10 KGs | 0.00007 | 0.0007 |
| 98 | Sampling bags (Zipper bags) 2000g capacity | - | 10 KGs | 0.00007 | 0.0007 |
| 99 | Round bottom long neck 800ml |  | 20 | 0.00007 | 0.0014 |
| 100 | Boron Free Flask |  | 12 | 0.042 | 0.504 |
|  |  |  |  |  | 6.433 |

Annexure XI

Cost Estimate for Establishment of Bioremediation Wastewater treatment facility at Peshawar

| S.No |  | QTY | Unit | Rate | Total (PKR) |
| --- | --- | --- | --- | --- | --- |
| 1 | Screening unit for removing solids/grits etc before entering the wetland as per design with flow control gate -brick masonry work | 96 | cft | 300 | 28,800 |
| 2 | Excavation in all kind of soil, rock, aggregate etc. hard and soft. Also re-arrange the excavated materials at sides and upstream to make a protection including carriage, compaction, dressing and leveling as per instruction of engineer in-charge. | 60000 | cft | 5.5 | 330,000 |
| 3 | Plastic lining through Laying geo membrane of 0.25 mm for Pond development including particle pitching and laying of earth to protect the sheets from up-lifting and bubbling also including dressing, leveling, sloping etc. complete in all respect. | 22,540 | Sft | 27 | 608,580 |
| 4 | Interconnecting RCC pipes of 1' for connecting all ponds as per design. Complete in all respect | 100 | Rft | 300 | 30,000 |
| 5 | Boulders (3''-6" Dia) for constructed wetland filling as filter media. Complete filling in wetland | 19,680 | cft | 65 | 1,279,200 |
| 6 | Crush Aggregate 0.5" | 1,500 | cft | 65 | 97,500 |
| 7 | Stone pitching (Boulders 8"-12") for stabilizing and fixing of plasting lining. Complete fixing on pond banks. | 1,000 | cft | 65 | 65,000 |
| 8 | Aquatic plants+ Installation+ Thermophore sheets | 1 | lumpsum | 100000 | 100,000 |
| 9 | Solar Pumping system (1 hp) along with pipe network | 1 | Nos | 100000 | 100,000 |
| 10 | Fence+Gate | 630 | Rft | 150 | 94,500 |
| 12 | Misc |  |  |  | 100,000 |
| Total |  |  |  |  | 2,833,580 |
| 13 | Technical Service Charges (includes visits and honorariums) |  |  |  | 300,000 |
| Grand Total |  |  |  |  | 3,133,580 |
| Grand Total (millions) |  |  |  |  | 3.134 |

| 1 | This estimate does not include wastewater collection or treated water distribution |  |
| --- | --- | --- |
| 2 | Rates are subject to change as per prevailing market conditions |
| 3 | The estimates are representative of a general bio radiation facility |

Annexure XII

Office Equipment and others

| S. No | Items | Quantity (Nos.) | Unit Price (Rs. M) | Total |
| --- | --- | --- | --- | --- |
| 1 | Inverter Split Unit (1.5 Tons) | 8 | 0.150 | 1.200 |
| 2 | Heavy duty Stabilizers | 12 | 0.080 | 0.960 |
| 3 | Water Dispenser (Electrical) | 2 | 0.060 | 0.120 |
| 4 | Smart TV 42 inches | 1 | 0.060 | 0.060 |
| 5 | Security Camera System (CCTV) | 1 | 1.000 | 1.000 |
|  | Total |  |  | 3.340 |

| District | Year 1 | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- |
| Peshawar | 13 | 20 | 20 | 53 |
| Charsadda | 10 | 21 | 16 | 47 |
| Mardan | 05 | 17 | 17 | 39 |
| Swabi | 07 | 13 | 14 | 34 |
| Noushera | 10 | 20 | 20 | 50 |
| Haripur | 05 | 15 | 15 | 35 |
| Abbottabad | 07 | 12 | 14 | 33 |
| Manshera | 07 | 12 | 14 | 33 |
| Kohat | 07 | 13 | 13 | 33 |
| Bannu | 05 | 07 | 07 | 19 |
| DI Khan | 05 | 10 | 10 | 25 |
| Swat | 14 | 30 | 30 | 74 |
| Buner | 05 | 10 | 10 | 25 |
| Grand Total |  |  |  | 500 |

Pesticide residue assessment plan in fruits and vegetables.

*The waste water and vegetables samples collection are subject to the seasonal availability and mobility.

| District | Year 1 | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- |
| Peshawar | 25 | 30 | 30 | 85 |
| Charsadda | 15 | 25 | 25 | 65 |
| Mardan | 10 | 35 | 35 | 80 |
| Swabi | 15 | 25 | 25 | 65 |
| Noushera | 15 | 25 | 25 | 65 |
| Haripur | 10 | 30 | 30 | 70 |
| Abbottabad | 15 | 25 | 25 | 65 |
| Manshera | 10 | 25 | 25 | 60 |
| Kohat | 10 | 20 | 20 | 50 |
| Karak | 05 | 15 | 15 | 35 |
| Bannu | 10 | 20 | 20 | 50 |
| DI Khan | 10 | 25 | 25 | 60 |
| Chitral | 10 | 20 | 20 | 50 |
| Dir lower | 10 | 20 | 20 | 50 |
| Dir Upper | 10 | 20 | 20 | 50 |
| Swat | 20 | 40 | 40 | 100 |
| Grand Total | 200 | 400 | 400 | 1000 |

Fertilizer/pesticide samples collection and analysis plan

*Fertilizer/pesticide samples collection are subject to the law and order situation, mobility.

| District | Year 1 | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- |
| Peshawar | - | 30 | 31 | 61 |
| Charsadda | - | 20 | 15 | 35 |
| Mardan | - | 20 | 20 | 40 |
| Swabi | - | 30 | 30 | 60 |
| Noushera | - | 20 | 20 | 40 |
| Haripur | - | 20 | 20 | 40 |
| Abbottabad | - | 14 | 13 | 27 |
| Manshera | - | 14 | 13 | 27 |
| Kohat | - | 13 | 12 | 25 |
| Bannu | - | 14 | 14 | 28 |
| DI Khan | - | 21 | 28 | 49 |
| Swat | - | 14 | 14 | 28 |
| Buner | - | 20 | 20 | 40 |
| Grand Total |  |  |  | 500 |

Heavy metals assessment plan in waste water, soil and vegetables from major cities.

*The waste water and vegetables samples collection are subject to the seasonal availability and mobility.

EXISTING FACILITIES VS PROJECT FACILITIES

Bio-Chemistry:

| S. No. | Existing Facilities | Strengthening Project Equipment received | Strengthening Project Equipment to be received | Surveillance Project Equipment to be received |
| --- | --- | --- | --- | --- |
| 1 | Electrical Balance | Furnace | Nitrogen analyzer | - |
| 2 | Oven | Centrifuge | Analytical Balance | - |
| 3 | Hot Plate | - | - | - |
| 4 | Shaker | - | - | - |
| 5 | Soxhlet | - | - | - |
| 6 | Kjheltech | - | - | - |
| 7 | Water Distillation Unit | - | - | - |
| 8 | Furnace | - | - | - |
| 9 | Centrifuge | - | - | - |

Soil Micro Biology:

| S. No. | Existing Facilities | Strengthening Project Equipment received | Strengthening Project Equipment to be received | Surveillance Project Equipment to be received |
| --- | --- | --- | --- | --- |
|  | Luminar Flow unit | Luminar Flow unit | Analytical balance | - |
|  | Autoclave | Autoclave | - | - |
|  | Incubator | - | - | - |
|  | Electrical Balance | - | - | - |
|  | Refrigerator | - | - | - |
|  | Oven | - | - | - |
|  | Water Distillation Unit | - | - | - |
|  | Micro Scope | - | - | - |
|  | Colony Counter | - | - | - |

Meteorology Section:

| S. No. | Existing Facilities | Strengthening Project Equipment received | Strengthening Project Equipment to be received | Surveillance Project Equipment to be received |
| --- | --- | --- | --- | --- |
|  | Sunshine recorder | Weather Station | Nil | - |
|  | Soil thermometer | - | - | - |
|  | Pane evaporation tub | - | - | - |
|  | Wet and Dry Bulb thermometer | - | - | - |
|  | Max. and Min. Thermometer | - | - | - |
|  | Anemometer | - | - | - |
|  | Rain Gauge | - | - | - |

Soil Section:

| S. No. | Existing Facilities | Strengthening Project Equipment received | Strengthening Project Equipment to be received | Surveillance Project Equipment to be received |
| --- | --- | --- | --- | --- |
|  | Flame Photometer | Flame Photometer | - | ICP-OES |
|  | Spectrometer | Spectrometer | - | Flame Photometer |
|  | pH meter | pH meter | - | Spectrometer |
|  | EC meter | EC meter | - | pH meter |
|  | Analytical Balance | Analytical Balance | - | EC meter |
|  | Hot Plate | - | Hot Plate | Analytical Balance |
|  | Drying Cabinet | - | Drying Cabinet | Kjeldhal Apparatus |
|  | Leaf Grinder |  | - | Drying Cabinet |
|  | Soil Grinder |  | - | Automatic Burette |
|  | Distillation Unit | - | Distillation Unit | Top Bottle Dispenser |
|  | Oven | - | - | Microwave Digester |
|  | Furnace | - | - | Soil Dispersion Machine |
|  | Grinding Mill | - | Grinding Mill | Electric /Horizontal Shaker |
|  | RO Plant | - | - | Furnace |
|  | - | - | Atomic Absorption | Oven |
|  | - | - | - | Grinding Mill |
|  | - | - | - | Lab Environment Monitoring Devices |
|  | - | - | - | Fume hoods, Blower/Exhaust System |
|  | - | - | - | Tool kits for lab and Field Activities |
|  | - | - | - | Personal Protection/Safety Equipment |
|  | - | - | - | Solvent Fraction Distillation Assembly/Unit |
|  | - | - | - | Lab Trolley with Wheels |
|  | - | - | - | Garmin GPS |
|  | - | - | - | Hydrometer |
|  | - | - | - | Electric /Horizontal Shaker |
|  | - | - | - | (Cathode Lamps) |

Pesticide Section:

| S. No. | Existing Facilities | Strengthening Project Equipment received | Strengthening Project Equipment to be received | Surveillance Project Equipment to be received |
| --- | --- | --- | --- | --- |
|  | Intuvo GC- System (9000) | Centrifuge | - | HPLC with DAD detector |
|  | GC-MS System (7890B) | Horizontal shaker | - | LC MS/MS |
|  | Spectra System UV(1000)HPLC | Dust absorber | - | Bottle top dispenser |
|  | Oven | - | - | Concentrator Nitrogen Jet Assembly |
|  | Cycling Vibrator | - | - | Safety Cabinets |
|  | GPC System | - | - | Lab Environment Monitoring Devices |
|  | Balance AEM-5200 | - | - | Fume hoods, Blower/Exhaust System |
|  | Analytical Balance | - | - |  |
|  | Electronic Balance | - | - | Tool kits for lab and Field Activities |
|  | Vortex Mixer | - | - | Personal Protection/Safety Equipment |
|  | Conductivity Meter | - | - | Blender/Mixture for Laboratory |
|  | Electronic Titrator | - | - | Nitrogen Generator |
|  | Centrifuge | - | - | Solid Phase Extraction manifold |
|  | Nitrogen Generator | - | - | -86 0C Freezer |
|  | - | - | - | Water bath |
|  | - | - | - | Rapid field pesticide residue test kits |
|  | - | - | - | Lab Trolley with Wheels |
|  | - | - | - | Garmin GPS |
|  | - | - | - | Digital pH meter |
|  | - | - | - | Electric /Horizontal Shaker |
|  | - | - | - | (Cathode Lamps) |